# SDEM® 2.0 Getting Started Guide

This training course is intended for those who selected "SDEM 2.0 Getting Started Guide," for those not

familiar with SDEM including the old SDEM, in the SDEM 2.0 Introductory Training.

## 1. What is SDEM?

What you will understand by the end of this chapter

- Why standardization is required in system development

- What is SDEM, Fujitsu's standard process structure

Chapter 1 explains what SDEM is.

By the end of this chapter, you will understand why standardization is required in system development and

what is SDEM, Fujitsu's standard processes.

### 1.1 Need for Standardization - Why Standardization is Required -

To build quality, the processes for planning, design, implementation,

and testing must be done in the correct order.

To provide customers with systems they can use with peace of mind,

an architecture for work at the same quality by many parties is required.

Standardization

First is an explanation of why standardization is required in system development, operation, and

maintenance.

To create high quality in systems, the processes for planning, design, implementation, and testing must be

done in the correct order.

In addition, to provide customers with systems they can use with peace of mind, an architecture for work at

the same quality by many parties is required.

The standardization of processes and the development architecture allows many parties to work at the same

quality in the correct order.

Examples of standardization are:

- "standard processes" that define work contents and procedures, and

- "standard documents" that define the formats and rules of design, management, and other documents.

### 1.1 Need for Standardization - Non-Standardized State -

Quality varies depending on the person

Work that should be done and descriptions in documents are omitted

Interfaces are incoherent and do not work well together

Maintainability is not good at the time of design change or repair after operation

So what kind of problems occur when processes and documents are not standardized?

For example, the following problems occur:

- Quality varies depending on the person

- Work that should be done is omitted

- Interfaces are incoherent and do not work well together

To prevent such problems, the required work and deliverables must be clarified. Standardization, that is, the

processes and architecture in place, is important to ensure that the required work is carried out properly,

even by those without experience.

### 1.1 Need for Standardization - Effects of Standardization -

Effect 1 - Work and quality are independent of people.

Effect 2 - Even inexperienced members understand the correct procedures for manufacturing with good quality.

Effect 3 - Information can be accurately transmitted without omission to the people in each role.

Effect 4 - Maintainability during operation and maintenance is improved by the handover of documents that comply with development standards.

Various effects can be expected from standardization.

Firstly, when the documents created with the standard documents, the items written in them, and the

required work are defined, you can prevent a dependence on the individual in work and quality.

Secondly, when the required work and its procedures are shown as standard processes, even

inexperienced members can carry out manufacturing in the correct order.

Thirdly, when the role division and required work in standard processes are clarified, you can convey

information accurately and without omission and unify how it is understood by the parties concerned.

Fourthly, after documents created using standard documents are handed over for operation and

maintenance, everyone understands what is written and where it is, which improves maintainability.

The next page explains what kind of standardization is underway at Fujitsu.

### 1.2 Fujitsu Standardization = Standard Process Structure "SDEM"

Fujitsu's standard process structure "SDEM"

- Systematizes the basic concepts and elements of planning, development, operation and maintenance, and quality assurance activities in Fujitsu's system development as standard processes

- Comprehensively systematizes the who, what, when, and what order of work to prevent omissions and ensure quality

- Gives a bird's-eye view of the whole like a map so that users understand their positions in it and communicate in a common language with the parties concerned

Fujitsu's standard process structure is called "SDEM."

It shows the basic concepts of planning, development, operation and maintenance, and quality assurance activities for systems handled by Fujitsu.

It is a bible for comprehensively systematizing the who, what, when, and what order of work to prevent omissions and ensure quality.

By using SDEM, you can get a bird's-eye view of the whole like a map and understand your position in it. So you will be able to communicate in a common language with the parties concerned.

### 1.3 Support for Global/De Facto Standards

Systematization based on global/de facto standards such as ISO/IEC/JIS, Common Frame, PMBOK, and ITIL, and Fujitsu's practical know-how

SDEM has been systematized by incorporating various domestic and global standards, such as Common

Frame and ITIL, in addition to Fujitsu's conventional practical know-how.

As a result, it can be used for projects that require compliance with global standards.

### 1.4 History of Standardization at Fujitsu

Created in 1976, SDEM has more than 40 years of accumulated knowledge,

a compilation of Fujitsu's know-how, and is still evolving along with global trends.

#### 1980

Software Development standards SDEM

SP to ME

#### 1990

System development Standards SDEM ® 90

SP, SA to OT, ME

#### 1995

System development standards SDEM ® 90 [Common Frame supported]

Contract work

System development work

SP, SA to OT, ME

Quality assurance work

Organizational improvement work

System audit work

#### 1999

Standard process structure for solution oriented planning, development, operation, and maintenance SDEM ® 21

| Contract process |  |  |
| --- | --- | --- |
| Planning process VP, SP | Development process SA to OT | Operation & maintenance process OM |
| Organizational management process |  |  |
| System audit process |  |  |

#### 2000

| Standard process structure for planning, development, operation, and maintenance SDEM® |  |  |  |  |
| --- | --- | --- | --- | --- |
| Planning process VP, SP | Requirement definition process RD | Development process UI to ST | Operational test & transition process OT | Operation & Maintenance process OM |
| Organizational management process |  |  |  |  |
| System audit process |  |  |  |  |

#### 2007

#### 2021

#### Since ‘18 - IPA

SEC BOOKS: User's Guide for Successful System Reconstruction

Points for Success in System Reconstruction

Updated on premise that "it is natural for existing systems to exist"

- Tacit knowledge from those experienced in reconstruction, turned into explicit knowledge, reconstruction work process expanded and systematized

- WBS refined to match actual situations of projects so that standards are more practical

Fujitsu's SDEM has more than 40 years of accumulated knowledge, which continues to be used in the field as a compilation of Fujitsu's know-how.

Here is a brief explanation about its history.

SDEM was born in 1976.

The purposes were to break away from development practices that depend on individual skills, and to curb the ever-increasing development costs.

In 1995, SDEM supported the common framework established as an industry standard in Japan. At the time, not only system development but also contract and organizational work was added, creating a prototype for

the current SDEM processes.

Since then, SDEM has continued to incorporate elements of international and de facto standards, responding to changes in the environment surrounding system construction.

In 2021, it was reformed into SDEM 2.0.

The main theme of SDEM up to then was "creating a new system."

However, it is now commonplace to have an existing system.

Therefore, SDEM was updated on the premise that "it is natural for existing system to exist."

SDEM will continue to evolve in the future.

## 2. SDEM Structure

What you will understand by the end of this chapter

- What are SDEM categories, phases, and WBS

Chapter 2 explains the SDEM structure.

By the end of this chapter, you will understand the SDEM categories, phases, and WBS.

### 2.1 SDEM Processes

[Project processes]

SDEM is systemization dividing system planning, development, and operation and

maintenance into 8 processes.

Contract process

Engage in contract work between purchaser and supplier

Requirement

definition process

Confirm requests from

users, etc. to system

based on IT strategy, and

define system

requirements as inputs for

system development

Planning process

Formulate IT strategy

closely aligned with

management strategy

Development process Operational test &

transition process

Operation &

maintenance process

Efficiently and reliably

realize system

requirements as system

Use system created in

development process for

users' operational tests,

production decisions, and

migration to new

business/system

Maintain, evaluate, and

improve system so that

users can smoothly carry

out their duties

[Organizational processes]

Organizational management process

Manage organization to efficiently and effectively support projects to achieve organizational goals

System audit process

A system auditor independent of the audit target evaluates whether or not IT system-related risks are properly controlled.

* In Japan, the system audit process is based on the system audit standards, system management standards, and so on established by the Ministry of Economy, Trade and Industry. SDEM

does not specify the contents of the process.

* This training course explains the processes from planning to operation & maintenance. For the contract, organizational management, and system audit processes, see the

Standard Process Guide for SDEM 2.0.

First is an explanation of the SDEM process structure.

The SDEM processes are broadly divided into project processes and organizational processes.

The project processes consist of processes for the system life cycle and the contract process. The

processes for the system life cycle consist of five processes: planning, requirement definition, development,

operational test & transition, and operation & maintenance.

The organizational processes are processes handled by the organization to support a project, and they

consist of the organizational management process and system audit process.

This training course explains the processes from planning to operation & maintenance, which are related to

the system life cycle.

For the contract, organizational management, and system audit processes, see the Standard Process Guide

for SDEM 2.0.

Chapter 4 introduces the Standard Process Guide.

13

### 2.2 Process Structure

Here is an explanation of the structure of the SDEM processes.

The SDEM structure is a matrix with two axes: categories on the vertical axis, and phases on the horizontal

axis.

The vertical axis shows the "required knowledge/skills" categories, and the horizontal axis shows the

phases, which are the time axis.

"Work to be done" is defined at the intersection.

The vertical axis clarifies "who," the horizontal axis clarifies "when," and the intersection clarifies "what."

The subsequent pages explain the vertical axis "Categories" first, the horizontal axis "Phases" next, and

"work to be done" finally.

14

### 2.3 Categories - Categories in Each Process –

Categories defined for each process

● Main categories of the work required to carry out each process

● Categories based on work relevance and the relevance of knowledge/skills required for work

| Planning process | Requirement definition process Development process Operational test & transition process | Operation & maintenance process |
| --- | --- | --- |
| A: Business management B: Business C: System usage D: System E: Project management | A: Business management T: Quality assurance (Overall test) B: Business C: System requirements D: Application E: Application infrastructure F: System infrastructure G: Operation and maintenance H: Transition & deployment I: Development support J: Project management | A: Business management B: Business C: IT service management D: System operation and maintenance E: Infrastructure provision G: Project management |

First is an explanation of the Categories vertical axis.

There are the main categories of work required to carry out each process. The categories are based on work

relevance and the relevance of knowledge/skills required for work.

Therefore, they can be useful for teaming in a project, as an example.

The categories have been appropriately defined based on the characteristics of the planning process, the

requirement definition, development, operational test & transition processes, and the operation &

maintenance process.

15

### 2.3 Categories - System as Combination of Many Technologies -

A system is a combination of many technologies.

A system is a "castle" made up of many technologies in a stack.

Architecture for connecting and moving everything

Important! System does not work until it is all put together

Starting with this page, here is a further explanation of the categories in the requirement definition, development, operational test & transition processes, which are the processes of system construction.

First of all, as a premise, a system is made up like this castle with many technologies in a stack. Be aware that an architecture for connecting and moving everything is important, and that the system does not work

until it is all put together.

16

### 2.3 Categories - Correspondence Between System and Categories –

Categories in requirement definition/development/operational test & transition process

A: Business management

T: Quality assurance (Overall test)

B: Business

C: System requirements

D: Application

E: Application infrastructure

F: System infrastructure

G: Operation and maintenance

H: Transition & deployment

I: Development support

J: Project management

The system structure corresponds to the categories in the requirement definition, development, and

operational test & transition processes.

One category corresponds to "what customers want to achieve" and others correspond to "work required in

system construction/operation" as roles required for system construction. There are other categories as well

corresponding to parts of the system structure.

Each category is classified by adding an alphabet letter; for example, "A: Business management" and "B:

Business."

Chapter 3 explains the contents of each category.

17

### 2.4 Phases - Time Divisions in System Life Cycle –

"Work to be done" by stakeholders involved in the system, mapped to the time axis of system construction.

Time period in the system life cycle, and unit for verifying a series of activities in system development.

● Phases in each process

| Process | Planning Process |  | Requirement Definition Process |  | Development Process |  |  |  |  |  |  | Operational Test and Transition Process | Operation and Maintenance Process |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Main Phase | Planning |  | Requirement Definition |  | Design |  | Implementation |  |  | Test |  | Operational Test and Transition | Operation and Maintenance |
| Phase | IT Vision Planning | System Planning | Current Business and System Analysis | System Resource Definition | User Interface Design | System Structure Design | Program Structure Design | Programming | Program Test | Integration Test | System Test | Operational Test and Transition | Operation and Maintenance |
| Abbreviation | VP | SP | CA | RD | UI | SS | PS | PG | PT | IT | ST | OT | OM |

Next is about the phases.

The SDEM phases are "work to be done" by stakeholders, such as our customers and us, and they are

mapped to the time axis of system construction.

They are time divisions throughout the life cycle of such a system, from planning, requirement definition,

design, implementation, test, and operational test and transition to operation and maintenance. They are

also units for verifying the progress and quality of the work in system development.

Memorize the abbreviations at the bottom of this table because they are often used to represent the phases.

18

### 2.4 Phases - V-shaped Model for Quality Assurance in System Development -

● Entire development process

● Provide quality assurance by gradually decomposing and creating system components, and gradually integrating and verify them in testing

● Match the system components at the requirement definition/design stage and the test stage, and verify and confirm quality with the V-shape (V-shaped model for quality assurance)

|  | Planning |  | Requirement Definition |  | Design |  | Implementation |  |  | Test |  | Operational Test and Transition | Operation and Maintenance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | VP | SP | CA | RD | UI | SS | PS | PG | PT | IT | ST | OT | OM |
| Business | Enterprise | Evaluation by top management <------------------------------------------------------------------------------------------------------------------------------------> Evaluation |  |  |  |  |  |  |  |  |  |  | Enterprise |
|  |  | Business |  |  | Validation by users <--------------------------------------------------------------------------------------> Validation |  |  |  |  |  |  | Business |  |
| System |  | System |  |  | System | Verification by designer <------------------------------------------------> Verification |  |  |  |  | System |  |  |
|  |  |  |  |  |  | Process | Verification by developers <--------------------> Verification |  |  | Process |  |  |  |
|  |  |  |  |  |  |  | Program module |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | System component |  |
|  |  |  |  |  | Gradually decompose in requirement definition/design |  |  |  |  | Gradually integrate in testing |  |  |  |

Here is an explanation of how the entire development process is systematized.

In SDEM, as the requirement definition, design, and implementation phases progress, the target system

components are gradually refined and decomposed in the order of business, system, process, and program.

In the test phase, the decomposed system components are integrated in the reverse order of process,

system, and business for verification.

Then, those same components are matched and verified in opposing phases for quality assurance.

For example, in the ST phase test, verify that the system is as designed in the UI phase. In the OT phase

test, the user validates that the requirements defined for business in the RD phase are satisfied.

This is the concept of the V-shaped model for quality assurance.

19

### 2.5 WBS (Work Breakdown Structure) - What is WBS? –

Hierarchization of "work to be done" in 3 stages

WBS1 level WBS2 level WBS3 level

[Systematization]

Most comprehensive

project management

[Refinement]

Input units of development resources

Role units of project members

[Substantiation]

Units of deliverables created

WBS code structure Sub category*1 + phase*2 + serial number*3 + 00 Level-1 code + serial number*3 + 0 Level-2 code + serial number*

3

*1 If no sub category, use "Main category + 1"

*2 If across phases/categories, use first phase/category

*3 1 to 9. Thereafter, A to Z

File structure Unit of standard filing for categories and phases

File code structure Level-1 code + f + serial number*3

Level-2 code + t + serial number*3

Level-3 code + d + serial number*3

Unit that bundles documents for WBS2 level Output for WBS3 level

C3UI100

Specification definition of

functional requirements (data)

C3UI110

Database logical design

C3UI120

File logical design

C3UI111 Definition of relationships between tables

C3UI112 Development of logical table lists

C3UI113 Detailed design of logical tables

C3UI114 Index design

C3UI121 Development of file lists

C3UI122 Detailed design of files

Here is an explanation of WBS.

"WBS" stands for Work Breakdown Structure, which is the structure of "work to be done" for each phase and

category.

SDEM hierarchizes it in three stages.

The WBS1 level is the systematization level, which provides an overall picture for comprehensive project management.

The WBS2 level is the refinement level, which refines the WBS1 work as the role units of project members.

The work here is also a unit for drawing up a detailed project schedule.

The WBS3 level is a more specific version of work at the WBS2 level.

Basically, the work here is a unit for creating deliverables.

The WBS of each layer is represented by assigned WBS codes indicating a category and phase.

20

### 2.5 WBS - Extended WBS Across Categories –

In system development, some work needs consideration from an overall perspective across SDEM categories.

"Z" is used in the IDs of items requiring consideration across categories.

Example 1:

Z1CA200 Confirmation of reconstruction requests and

tentative definition of reconstruction pattern from requests

perspective

Requiring consideration from an overall perspective across

all categories

Example 2:

DZCA100 Overall understanding of current assets

Requiring consideration across sub categories in Category D

Copyright 2022 FUJITSU LIMITED

"Z" indicates work requiring consideration from an overall perspective across categories.

[List of CA phase work items (WBS1)]

In system development, some work needs consideration from an overall perspective across SDEM categories.

For that work, the letter "Z" is used in the category part of the WBS code.

21

### 3. Each SDEM Process

What you will understand by the end of this chapter

- Definition and workflow of every phase in each SDEM process

- Role of each category of the SDEM requirement definition/development/operational test & transition process

Chapter 3 explains each SDEM process.

By the end of this chapter, you will understand the definition and workflow of each phase, and the role of

each category.

22

### 3.1 Planning Process

Section 3.1 is about the planning process.

This section explains the definition and workflow of each phase.

### 3.1 Planning Process - IT Vision Planning [VP] Phase –

Investigate and analyze the current enterprise environment and business to define IT vision goals and measures.

Understand enterprise environment and business.

◼ Understand business policy and current business, and extract issues

Understand enterprise environment, current business, current system outline, restrictions, etc., and identify issues.

Define IT vision.

◼ Plan IT system vision

- Define measures and initiative themes

- Systematize from IT system perspective, consider feasibility and priority, and plan IT system vision

System

planning

Input information Work item Work item in next phase

Medium-term

management

strategy

Business

plan

Top management

Business

personnel

Top management

Business

personnel

The planning process includes the VP phase and SP phase. First, here is an explanation of the IT vision planning [VP] phase.

The purposes of the VP phase are to understand the current enterprise environment and business, and to

clearly define the IT vision.

The VP phase defines measures and initiative themes based on the management policy and business policy, taking current issues into account.

Then, the overall consistency, feasibility, and priority are considered from the IT system perspective and

summarized as the IT system vision.

24

### 3.1 Planning Process - System Planning [SP] Phase -

Based on the IT system vision, define new business requirements, estimate the ROI, and make decisions for system development

Define business requirements and system requirement outline

◼ Define business requirements and system requirement outline

- Take inventory of current system, and define new

business requirements and system requirement outline

- Formulate basic configuration plan for new system

Develop system plans.

◼ Develop system plans.

- Estimate IT investment costs and verify ROI

- Develop overall system plan

- Develop project execution plan and pass it on to

requirements definition process

Work item Work item in previous

phase Work item in next phase

Business

personnel

Top management

Top management

Business

personnel

Define IT

vision

Analyze current

business and

system

Here is an explanation of the system planning [SP] phase.

The purposes of the SP phase are to clarify what kind of system should be constructed and to define new

business requirements based on the IT system vision.

Agreement on the purpose and effects of the developed system is required of the parties concerned, in

consideration of the market and technology trends.

The SP phase defines new business requirements and system outline requirements, determines the overall

picture of the new system, and formulates a basic configuration plan for the new system.

The costs are estimated, including the system development and operational costs of the next phase, and the

ROI is verified based on the resulting estimates.

These are considered in the development of the overall system plan and project execution plan.

25

In business transformation utilizing the latest digital technologies, that is, DX, IT human resources familiar

with digital technologies need to participate from the company-wide strategy planning and business strategy

planning stages, not from the planning process.

Customers should play the main role in developing the company-wide strategy and business strategy.

However, as a DX partner, we should understand the customers' ideas and provide support as an IT expert.

Business & IT Grand Design Process Structure [BIeDP] systematizes the work processes and knowledge for

the DX vision/planning.

Since it is provided in the SDEM Technical Content, use it to support the customers' DX vision/planning.

Chapter 4 introduces the SDEM Technical Content.

Copyright 2022 FUJITSU LIMITED 26

SDEM

planning process

VP/SP phase

[Reference] Business & IT Grand Design Process Structure [BIeDP*]

Copyright 2022 FUJITSU LIMITED

Strategy planning System planning

* BIeDP is included in the SDEM Technical Content. Chapter 4 introduces the SDEM Technical Content.

* BIeDP:

Business & IT Enterprise Design Process

Systematize the work processes and knowledge for the DX vision/planning

SDEM Technical Content

Business & IT Grand Design Process

Structure [BIeDP]

Business

strategy

Grand

design

26

Section 3.2 explains the requirement definition process, development process, and operational test &

transition process.

This section explains the roles of the categories, and then the definition and workflow of each phase.

Copyright 2022 FUJITSU LIMITED 27

3.2 Requirement Definition/Development/Operational Test &

Transition Process

27 Copyright 2022 FUJITSU LIMITED

Here is an explanation of the categories.

This page is about Categories A, T, and B. Categories A and T play the role of "Overall control" in system

development, and Category B corresponds to "What customers want to achieve in business."

Category A is "Business management," which is to judge the ROI, determine the project startup, pause,

transition, and completion, as well as organize and arrange organizations from the viewpoint of business

management.

The customer's top management is in charge of this category because it should be done from the viewpoint

of business management.

The sub categories subdivided from the main categories include "Business management" and

"Organization."

Category T is "Quality assurance (Overall test)," which is to promote the overall test and manage quality for

the following purposes for production: risk measures at project startup, and early risk measures during the

project.

It is important to work on this category with the customer and vendors as an entire project.

The sub categories are "Business operation continuity judgment criteria," "Quality assurance achievement

level," "Quality assurance scenario," "Overall test plan and execution," and "Individual test plan."

Category B is "Business," which is to establish business specifications and perform business operational

tests from the viewpoint of users. This category determine the specific business the customers want to

achieve.

The sub categories are "Business operation," "Business function," and "UX (Usage experience)."

Copyright 2022 FUJITSU LIMITED 28

Categories A and T correspond to "Overall control" and

Category B corresponds to "What customers want to achieve in business."

Infrastructure

Servers Storage Networks

System

infrastructure

OS

Middleware

Application

infrastructure

Applications

What

customers

want to achieve

(Business)

Cloud

Frameworks

Common parts

Operational

infrastructure Operations Architecture for connecting and moving everything

3.2.1 Requirement Definition/Development/Operational Test &

Transition Process Categories (1)

Copyright 2022 FUJITSU LIMITED

Category

A: Business management

T: Quality assurance

(Overall test)

B: Business

C: System requirements

D: Application

E: Application

infrastructure

F: System infrastructure

G: Operation and

maintenance

H: Transition &

deployment

I: Development support

J: Project management

Main

Category

Description Sub Category

A: Business

management

Judge the ROI, determine project

startup, pause, transition, and

completion, as well as organize and

arrange organizations from the

viewpoint of business management.

A1: Business management

A2: Organization

T: Quality

assurance

(Overall test)

Promote overall test and manage

quality for the following purposes for

production:

- Risk measures at project startup

- Early risk measures during the

project

T1: Business operation

continuity judgment criteria

T2: Quality assurance

achievement level

T3: Quality assurance scenario

T4: Overall test plan and

execution

T5: Individual test plan

B: Business Establish business specifications and

perform business operational tests

from the viewpoint of users.

- Substantiate business requirements,

and determine business

specifications that the customer will

agree with.

- Design business operations, and

verify the operations as business.

B1: Business operation

B2: Business function

B3: UX (Usage experience)

Overall

control

28

Here is an explanation of Categories C to F. Category C corresponds to the architecture for connecting and

moving everything, and Categories D, E, and F correspond to the system structure from application to

infrastructure.

Category C is "System requirements," which is to design the overall system architecture for doing business

and then pass on that information to each category.

The sub categories are "Overall system architecture," "Functional requirements (System functions),"

"Functional requirements (Data)," "Functional requirements (Interface)," "Non-functional requirements," and

"Security."

Category D is "Application," which is to design, develop, and test applications.

The sub categories are "New application development and diversion development," "Package usage," and

"Migration (Source code conversion)" depending on the application development method.

Category E is "Application infrastructure," which is to design and provide common application functions

deployed as a common infrastructure.

The sub categories are "Application architectures (including frameworks)," "Database architectures and

definitions (Applications)," and "Application environment."

Category F is "System infrastructure," which is to design and provide the system configuration and

environment, network, databases, and system operations that are required for system implementation.

Category F also includes the infrastructure, OS, middleware, and operational infrastructure.

The sub categories are classified by elements for meeting non-functional requirements. They include

"Performance & scalability," "Reliability," "Security," "External connectivity," "System configuration &

environment," "Database," "Network," "Facility," and "System operation."

Copyright 2022 FUJITSU LIMITED 29

Category C corresponds to "Architecture for connecting and moving everything" and

Categories D, E, and F correspond to the system structure from applications to infrastructures.

3.2.1 Requirement Definition/Development/Operational Test &

Transition Process Categories (2)

Copyright 2022 FUJITSU LIMITED

Main

Category

Description Sub Category

C: System

requirements

Design the overall system

architecture for doing business

and then pass on that

information to each category.

C1: Overall system architecture

C2: Functional requirements (System

functions)

C3: Functional requirements (Data)

C4: Functional requirements (Interface)

C5: Non-functional requirements

C6: Security

D: Application Design, develop, and test

applications (including

packages).

D1: New application development and

diversion development

D2: Package usage

D3: Migration (Source code conversion)

E: Application

infrastructure

Design and provide common

application functions deployed

as a common infrastructure.

E1: Application architectures (including

frameworks)

E2: Database architectures and

definitions (Applications)

E3: Application environment

F: System

infrastructure

Design and provide the system

configuration and environment,

network, databases, and system

operations that are required for

system implementation.

F1: Performance & scalability

F2: Reliability

F3: Security

F4: External connectivity

F5: System configuration & environment

F6: Database

F7: Network

F8: Facility

F9: System operation

Category

A: Business management

T: Quality assurance

(Overall test)

B: Business

C: System requirements

D: Application

E: Application

infrastructure

F: System infrastructure

G: Operation and

maintenance

H: Transition &

deployment

I: Development support

J: Project management

Infrastructure

Servers Storage Networks

System

infrastructure

OS

Middleware

Application

infrastructure

Applications

What

customers want

to achieve

(Business)

Cloud

Frameworks

Common parts

Operational

infrastructure Operations Architecture for connecting and moving everything

29

Last is Categories G to J.

Category G corresponds to "Post-production preparation." Categories H, I, and J correspond to "Work

required in system construction/operation."

Category G is "Operation and maintenance," which is to prepare for operation and maintenance after

production. The only sub category is "Operation & maintenance."

Category H is "Transition & deployment," which is to plan and design transition and deployment, and

perform transition rehearsal and the actual transition.

The sub categories are "Transition plan," "Business system transition," "Data transition," and "Deployment."

Category I is "Development support," which is to provide support for smooth development practice, establish

development standards for overall project integration, and develop and operate a framework for

configuration management, tools, etc.

The sub categories are "Development standard" and "Configuration management."

Category J is "Project management," which is to develop project plans and establish goals such as deadline,

quality, and cost for production, and promote and operate the project.

There are eleven sub categories in total. "Integration management," "Scope management (Requirement

management)," "Time management (Progress management)," "Cost management (Profit and loss

management)," "Quality management (Quality and defects management)," "Human resource management

(Personnel management)," "Communications management (Information distribution and performance

report)," "Risk management (Risk control)," and "Procurement management (External procurement

management)" correspond to the knowledge area in the PMBOK 6th Edition. "Contract management

(Contracts with customers)" and "OSS application management" are unique to SDEM.

Copyright 2022 FUJITSU LIMITED 30

Category G corresponds to "Post-production preparation" and

Categories H, I, and J correspond to "Work required in system construction/operation."

3.2.1 Requirement Definition/Development/Operational Test &

Transition Process Categories (3)

Copyright 2022 FUJITSU LIMITED

Main Category Description Sub Category

G: Operation and

maintenance

Prepare for operation and

maintenance after production

(transition, etc.).

G1: Operation & maintenance

H: Transition &

deployment

Plan and design transition and

deployment, and perform transition

rehearsal and the actual transition.

H1: Transition plan

H2: Business system transition

H3: Data transition

H4: Deployment

I: Development

support

Establish development standards for

overall project integration, and

develop and operate a framework for

configuration management, tools,

etc.

I1: Development standard

I2: Configuration management

J: Project

management

Develop project plans and establish

project goals (deadline, quality, cost,

etc.) for production, and promote and

operate the project.

J1: Integration management

J2: Scope management (Requirement

management)

J3: Time management (Progress management)

J4: Cost management (Profit and loss

management)

J5: Quality management (Quality and defects

management)

J6: Human resource management (Personnel

management)

J7: Communications management (Information

distribution and performance report)

J8: Risk management (Risk control)

J9: Procurement management (External

procurement management)

JA: Contract management (Contracts with

customers)

JB: OSS application management

Category

A: Business management

T: Quality assurance

(Overall test)

B: Business

C: System requirements

D: Application

E: Application

infrastructure

F: System infrastructure

G: Operation and

maintenance

H: Transition &

deployment

I: Development support

J: Project management

Infrastructure

Servers Storage Networks

System

infrastructure

OS

Middleware

Application

infrastructure

Applications

What

customers

want to achieve

(Business)

Cloud

Frameworks

Common parts

Operational

infrastructure Operations Architecture for connecting and moving everything

Work required in system

construction/operation

Post-production

preparation

30

Each phase will be explained. First, the requirement definition process phase.

The requirement definition process includes the CA and RD phases. This page explains the current

business and system analysis [CA] phase.

The CA phase has three purposes.

The first is to determine if the requirement definition or development phase can begin, and make up for any

missing information.

The second is to determine the reconstruction pattern and eliminate any discrepancy in awareness between

the customer and us.

The third is to reach an agreement with the customer on possible risks in the previous phase and ideas on

hedging the risks.

In order to realize these purposes, analyze the current business, system, operations, and incompatibilities,

and evaluate the feasibility and determine the reconstruction pattern based on the investigation results.

Next, reach an agreement with the customer on risk.

In addition, for quality assurance after production, formulate the business operation continuity judgment

criteria and the quality assurance achievement levels.

Note that the reconstruction pattern means the reconstruction method such as rehost, rewrite, and rebuild.

Copyright 2022 FUJITSU LIMITED 31

3.2.2 Requirement Definition Process - Current Business and System

Analysis [CA] Phase -

Copyright 2022 FUJITSU LIMITED

Analyze the current situation, determine the development method, and reach an

agreement with stakeholders on risk

Current analysis

Formulate quality assurance scenario

◼ Formulate quality assurance scenario

Formulate business operation continuity judgment criteria

and quality assurance achievement levels

◼ Analyze current business and system

Analyze current business, system, operations

and incompatibilities

Develop

system plans

Define business

and system

requirements

(Reconstruction +

New)

Top management

Business personnel

Project manager

Work item in previous phase Work item Work item in next phase

Define system

requirement

outline

Define

business

requirements

(Continues to RD phase)

Agree on reconstruction pattern*/risk

◼ Agree on reconstruction pattern/risk

- Evaluate feasibility and determine reconstruction pattern based

on investigation results

- Reach agreement with stakeholders on risk

Business

Application

Application infrastructure

System infrastructure

Personnel

Top management

Project manager

Determine

reconstruction

pattern with new

requirements

⚫ Purposes of the CA phase

1.Determine if the requirement definition or

development phase can begin, and make

up for any missing information

2.Determine the reconstruction pattern and

eliminate any discrepancy in awareness

between the customer and us

3.Reach an agreement with the customer

about possible risks in the previous

phase and ideas on hedging the risks

* Reconstruction pattern: Reconstruction method such as rehost, rewrite, and rebuild

31

Here is an explanation of the system requirement definition [RD] phase.

The purposes of the RD phase are to define requirements and design the overall architecture, which are

required for system implementation, and reach an agreement with stakeholders.

Define the requirements for business operations and functions, integrating reconstruction requirements and

new requirements. System requirement definition is divided into functional requirements and non-functional

requirements. The functional requirements include those for system functions, data, and interfaces. The

non-functional requirements include those for performance and scalability, reliability, and security. In

addition, define the requirements for the overall system architecture.

Finally, confirm the reconstruction pattern determined in the CA phase, formulate the quality assurance

scenario and overall test plan, and reach an agreement with stakeholders on requirement definition.

Copyright 2022 FUJITSU LIMITED 32

3.2.2 Requirement Definition Process - System Requirement Definition

[RD] Phase -

Copyright 2022 FUJITSU LIMITED

Define requirements and design the overall architecture, which are required for system

implementation, and reach an agreement with stakeholders

Define system requirements (Reconstruction + New)

◼ Define functional requirements

Define requirements for system functions, data, and interfaces

◼ Define non-functional requirements

Define requirements for performance, scalability, reliability,

security, etc.

Analyze

current

business and

system

Design

configuration

Design

architecture

Design business

and system

specifications

Design

operations

Work item in previous phase Work item Work item in next phase

◼ Define overall architecture requirements

Define overall system architecture requirements

Business

Application

Application

infrastructure

System infrastructure

Personnel

Determine reconstruction pattern with new requirements

Agree on

reconstruction

pattern/risk

Formulate quality assurance scenario/overall test plan

Formulate quality

assurance

scenario

(Continued from CA phase)

Top management

Project manager

Define business requirements (Reconstruction + New)

◼ Define business requirements

Define requirements for business operations and functions

32

The explanations from here cover the phases of the development process. The development process

includes the phases from UI to ST.

First is an explanation of the user interface design [UI] phase.

The purposes of the UI phase are to design external system specifications from the user perspective, design

the architecture for system implementation, and reach an agreement with stakeholders.

In designing business and system specifications, substantiate the system functions, data, interfaces,

screens, and forms based on the requirement definition of the RD phase.

In addition, design the application architecture, design an architecture for ensuring performance, reliability,

etc., and determine the configurations of hardware, software, databases, etc.

Furthermore, as operation design, design the operation methods, etc. for stable, abnormal, or maintenance

operations.

Copyright 2022 FUJITSU LIMITED 33

Design external system specifications from the user perspective, design the architecture for system

implementation, and reach an agreement with stakeholders

3.2.3 Development Process - User Interface Design [UI] Phase -

Copyright 2022 FUJITSU LIMITED

Design architecture

Design business and system specifications

◼ Define functional requirement specifications

Substantiate specifications of system functions, data,

and interfaces

◼ Design application architecture

Substantiate processing methods such as screen control,

transition, and batch start mode

Define business and

system requirements

(Reconstruction +

New)

Set up

application

infrastructure

Design

structure

Application

Application

infrastructure

System infrastructure

personnel

Application

Application

infrastructure

personnel

(Continues to SS phase)

Work item in previous phase Work item Work item in next phase

Design operations

Design configuration

◼ Design architecture/system configuration for

performance, reliability, etc.

- Determine implementation methods for performance,

scalability, reliability, etc.

- Determine configurations of hardware, software, databases, etc.,

and network methods

Design

System environment

infrastructure

personnel

33

Here is an explanation of the system structure design [SS] phase.

The purpose of the SS phase is to design for system implementation.

In so doing, develop the design agreed upon with the stakeholders.

The design for implementation in this phase is based on the business and system specifications,

architecture design, configuration design, and operation design in the UI phase.

In designing the application structure, define the program divisions and functions.

In setting up the application infrastructure, create application infrastructure programs one stage earlier than

the start of business programming.

Then, in designing the environment, develop the environment design such as parameters related to

hardware and software installed in the system, develop the physical design of the databases, and so on.

Copyright 2022 FUJITSU LIMITED 34

3.2.3 Development Process - System Structure Design [SS] Phase -

Copyright 2022 FUJITSU LIMITED

Set up application infrastructure

Design structure

◼ Design application structure

- Divide process into programs in functional units

- Define program function outline

◼ Develop application infrastructure programs

Develop application infrastructure programs (Programming,

program test)

Application

infrastructure

personnel

Design

configuration

Design

architecture

Set up

environment

Implement

Design business

and system

specifications Application

personnel

Work item in previous phase Work item Work item in next phase

Design for system implementation, and confirm that the user interface design

reflects the specifications agreed upon

Design environment

◼ Design system environment, database, etc.

- Design system environment such as hardware and software

- Develop physical and environmental designs of databases,

and design network environment

System

infrastructure

personnel

Design operations

Design

operations

(Continued from the UI phase)

34

This and the next page explain the program structure design [PS] phase, programming [PG] phase, and

program test [PT] phase collectively as the implementation phase.

First is an explanation of application-related work.

The PS phase develops program structure designs, such as module division, and the detailed designs of

logic and algorithms to definitely incorporate the design results of the SS phase into programs.

The PG phase performs program coding.

The PT phase verifies the programs implemented in program units and ensures quality.

Copyright 2022 FUJITSU LIMITED 35

3.2.3 Development Process - Implementation Phase [PS to PT] (1) -

Copyright 2022 FUJITSU LIMITED

Create programs and ensure quality by verifying them in program units

Implement

◼Design

program

structure

Develop structural

designs, such as

module division,

and detailed

designs

◼Do

programming

Perform coding,

etc.

◼Test programs

Run tests on

programs

PS phase PG phase PT phase

◼Develop integration test specifications

Develop integration test specifications

Design

structure

Set up

application

infrastructure

Run

integration test

Application

personnel

Work item in previous phase Work item Work item in next phase

35

3.2.3 Development Process - Implementation Phase [PS to PT] (2) -

Copyright 2022 FUJITSU LIMITED

Set up and verify the system infrastructure environment

Test system

infrastructure

Set up environment

◼Install hardware and software,

and check operations

- Install hardware and software, and

configure their environment

- Develop system infrastructure test

specifications

◼Test system

infrastructure

[Up to IT]

Run tests on

system

infrastructure

◼Install database, etc.

- Install and configure database

environment, network devices, etc.

- Develop system infrastructure test

specifications

System

infrastructure

personnel

Design

environment

(Continues to test phase)

Design

operations

Work item in previous phase Work item Work item in next phase

PS phase PG phase PT phase

System

infrastructure

personnel

36

Here is an explanation of the system infrastructure work.

Set up the environment during the PS phase to PG phase.

Install hardware and software, set parameters, and install and configure the database environment, network

devices, etc.

In the PT phase, test the environment that has been set up. Run the system infrastructure test by the first

half of the IT phase.

Copyright 2022 FUJITSU LIMITED 36

This page explains the integration test [IT] phase and system test [ST] phase collectively as the test phase.

The purposes of the IT phase are to integrate programs whose quality was confirmed in the PT phase, and

to verify the quality of integrated functions and interfaces between functions.

First, run the integration test for the business applications overall.

Next, after the system infrastructure test is completed, run the integration test for the business applications

on the system infrastructure. Also, verify interface quality by integrating the business and infrastructure.

The purposes of the ST phase are to verify the overall system quality and to confirm the achievement of the

quality assurance achievement levels formulated together with the customer.

In the system test, verify the overall system from functional aspects, non-functional aspects such as

performance and reliability, and operational aspects. For the test, use the data and system environment

appropriate to the actual business operations if possible.

Copyright 2022 FUJITSU LIMITED 37

3.2.3 Development Process - Test Phase [IT to ST] -

Copyright 2022 FUJITSU LIMITED

Verify the quality of integrated functions and interfaces between functions [IT]

Verify the overall system quality, and confirm the achievement of the quality assurance

achievement levels [ST]

System infrastructure

test

Integration test

◼Integration test

Test functions of

business

applications overall

◼System

infrastructure test

[PT and later]

Test system

infrastructure

System test

◼System test

Run test

appropriate to

business operations

Verify overall

system

- Functionality

- Non-functionality

(Performance,

scalability,

reliability, etc.)

- Operation

Implement

(Continued from

implementation

phase)

Run

operational

test

Application

personnel

System

infrastructure

personnel

Work item Work item in

previous phase

Work item in next

phase

Integration test

(Business and

infrastructure

integration)

◼Integration test

Integrate business

applications and

infrastructure, and

test interfaces

IT phase ST phase

Application

Application

infrastructure

System

infrastructure

personnel

Application

Application

infrastructure

System

infrastructure

personnel

37

This page explains the operational test & transition process phase. The phase is operational test and

transition [OT].

The purposes of the OT phase are to make a business operation continuity judgment based on business

scenario verification results, etc., make production decisions based on that, and transition to the new

system.

As the operational test, users verify the business scenario. Based on the business operation continuity

judgment criteria and production agreed upon with the customer, determine if production is possible and if

transition to the new system is possible.

When there is no problem, perform transition and deployment of the system and data.

Copyright 2022 FUJITSU LIMITED 38

3.2.4 Operational Test & Transition Process - Operational Test and

Transition [OT] Phase -

Copyright 2022 FUJITSU LIMITED

Make production decisions based on a business scenario verification and

business operation continuity judgment to transition to the new system

Transition and

deployment

Transition decision

making

Operational test

◼ Operational test

and transition to

new business

- Users become familiar

with system and

understand problems

in business operations

- Switch from current

business to new

business

◼ Transition

decision

making

Evaluate whether

quality goal was

achieved, and

make decision on

transition

◼ Transition

Perform

transition of

system and data

User

◼ Deployment

Deploy

Top

management

System test

Transition and

deployment

personnel

Production

Work item in previous phase Work item

38

The explanations so far have covered the roles of categories of the SDEM requirement definition,

development, operational test & transition processes, and the definition and workflow of each of their

phases.

This diagram shows the main workflow in requirement definition, development, operational test & transition.

The explanations so far have mainly covered construction work and quality assurance. In addition to that,

preparation for operation and maintenance after production, work for transition and deployment,

development support, project management, and various other work have been defined.

Copyright 2022 FUJITSU LIMITED 39

Copyright 2022 FUJITSU LIMITED

Process/Phase

Category

Planning Requirement Definition Development

Operational

Test &

Transition

Operation &

Maintenance

VP SP CA RD UI SS PS PG PT IT ST OT OM

A: Business management

T: Quality assurance

(Overall test)

B: Business

C: System requirements

D: Application

E: Application

infrastructure

F: System infrastructure

G: Operation and

maintenance

H: Transition &

deployment

I: Development support

J: Project management

Define

enterprise

requirements

Define

business

requirements

(Outline)

Make

development

decisions

Define

business

requirements

Define

system

requirements

Design

system

specifications

Design

structure Implement Integration

test

System test Operational

test

Make

transition

decision

Design

configuration

and operations

Set up

application

infrastructure

Design

environment

Design architecture

Set up environment

Set up environment

System infrastructure

test

Prepare for transition and

deployment

Rehearse

and preverify

Transition

and deploy

Substantiate development standards and manage configuration

Execute, monitor, and control the project, and manage changes Develop the project

plan

Design

architecture

Analyze current business and system

Agree on reconstruction pattern/risk

Formulate quality assurance

scenario

Prepare for operation and

maintenance

Develop test plan

Integrate

business and

infrastructure

Develop transition

plan

Design

business

specifications

Understand

overall operation

and

maintenance

Understand Train users and operation/maintenance personnel

operational and

maintenance

requirements

Perform

operation

and

maintenance

3.2.5 Main WBS Flow of Requirement Definition/Development/Operational Test &

Transition Process

39

Section 3.3 explains the operation & maintenance process.

Copyright 2022 FUJITSU LIMITED 40

3.3 Operation & Maintenance Process

40 Copyright 2022 FUJITSU LIMITED

The operation & maintenance process includes only the operation and maintenance [OM] phase because it

has no concept of start and end like in a development project.

In the OM phase, develop a plan for safe and stable operation of the system, and regularly review and

improve the plan cyclically.

For daily operation and maintenance, go through a cycle centered on operation management, from business

operation, system operation, application maintenance, and infrastructure maintenance request to delivery.

Engage in integrated management from the perspective of management and business.

Copyright 2022 FUJITSU LIMITED 41

3.3 Operation & Maintenance Process - Operation and Maintenance

[OM] Phase -

Copyright 2022 FUJITSU LIMITED

C1: Integrated management (Operation and maintenance management, business continuity planning, etc.)

D1: Business operation

(Business monitoring, business

troubleshooting, business operation

document management, etc.)

D3: Application maintenance

(Application failure support, application

modification/specification change, data

maintenance, etc.)

D2: System operation

(System monitoring, system

troubleshooting, system operation

document management, etc.)

D4: Infrastructure

maintenance

(Hardware failure support, software

failure support, network failure support,

database environment change, etc.)

C2: Operational management

(Service desk, incident management,

problem management, operational

improvement, etc.)

Users (Manager/End users)

Software/Hardware vendors

Regular report

Support request

Support contract

Delivery

A: Business management (Business management, organization)

B: Business (Business operation)

Support contract

Delivery

Change request

collaboration

Change request

collaboration

Joint study

Release discussion

E1: Infrastructure provision (Facility provision/management, IT resource provision, etc.)

G: Project management (Scope management, time management, cost management, etc.)

Develop a plan for safe and stable operation of the IT system, and regularly

review and improve the plan

* A: Business management,

B: Business,

C1: Integrated

management, etc. are

categories.

41

Chapter 4 explains the SDEM content structure.

By the end of this chapter, you will understand the content provided with SDEM, types of SDEM practical

standards, which are part of it, and what is provided.

Copyright 2022 FUJITSU LIMITED 42

4. SDEM 2.0 Content Structure

Copyright 2022 FUJITSU LIMITED

What you will understand by the end of this chapter

- What kind of content is provided with SDEM

- Types of SDEM practical standards, and what is provided

42

SDEM broadly consists of the SDEM Standard Processes, the SDEM Practical Standards, and the SDEM

Technical Content.

The SDEM Standard Processes are a general-purpose work structure independent of industry, language,

development environment, and so on. It covers the overall work required for planning, development,

operation and maintenance, and quality assurance activities.

They contain three types of content: Standard Process Structure, WBS Manual, and Standard Process

Guide.

The SDEM Practical Standards are provided as more practical work standards for each field.

Document formats, samples, specific work procedures, and guides are provided.

The SDEM Technical Content contains technical know-how and document samples useful in practicing

Fujitsu project work.

Starting with the next page, the content provided in the SDEM Standard Processes is introduced.

Copyright 2022 FUJITSU LIMITED 43

4.1 Overall SDEM Structure

43 Copyright 2022 FUJITSU LIMITED

First is an explanation of the Standard Process Structure.

This content includes the WBS1 and WBS2 structures, categories, and phase definitions of the SDEM

standard processes.

Take advantage of the content to get an overall picture of the SDEM standard processes.

When estimating project work and planning role division, be sure to use this standard process structure.

In addition, WBS1, WBS2, and WBS3 lists are provided in CSV format. Use them for project standardization,

WBS name extraction in schedule creation, etc.

Copyright 2022 FUJITSU LIMITED 44

4.2 SDEM Standard Processes - Standard Process Structure -

● SDEM (WBS1-2 structure) key point summary

Copyright 2022 FUJITSU LIMITED

[Planning, requirement definition, development, operational test &

transition, operation & maintenance process WBS1]

[Explanation of categories and phases]

⚫ WBS1-2 provided

⚫ Printable (A3) files also provided

⚫ WBS data in CSV format also provided

(WBS1-2-3)

Use for project planning (estimation, schedule creation, role

division), etc.

Use to:

- Collect detailed tasks

- Extract the WBS name in schedule creation

44

Next is about the WBS Manual in the SDEM Standard Processes.

This content is provided in WBS2 units.

It shows what to input or output in each WBS, and the key points of work and viewpoints for consideration

for WBS3 individually.

Use it to understand work you are experiencing for the first time, and so on.

This content also includes the WBS purpose.

When performing work, it is important to understand the purpose of the work.

When reading the WBS Manual, pay attention to this purpose to deepen your understanding.

Copyright 2022 FUJITSU LIMITED 45

4.2 SDEM Standard Processes - WBS Manual -

● Explanation of key points of work in each WBS

Copyright 2022 FUJITSU LIMITED

* The WBS Manual is not provided for Categories C

to E in the operation & maintenance process

(OM).

See the SDEM Practical Standards: Operation and

Maintenance (ITSMOP).

⚫ Provided in WBS2 units

⚫ Describes the WBS purpose and input/output

⚫ Describes key points of work and viewpoints for

consideration for WBS3 individually

Use to:

- Understand the procedure and viewpoints of

work you are in charge of

- Get reviewers and auditors to check if they

missed some checks

45

The third type of content in the SDEM Standard Processes is the Standard Process Guide.

This page shows the table of contents of the guide.

This content explains each SDEM process and the concepts of SDEM application methods.

The Standard Process Guide has been divided into an internal version and the FUJITSU-CONFIDENTIAL

version. The internal version explains the key points to progressing smoothly in a project.

Read it if you want to understand these points or want to understand SDEM in more detail than provided in

this training course.

These pages have explained the Standard Process Structure, WBS Manual, and Standard Process Guide in

the SDEM Standard Processes.

Next is an explanation of the SDEM Practical Standards.

Copyright 2022 FUJITSU LIMITED 46

4.2 SDEM Standard Processes - Standard Process Guide -

Copyright 2022 FUJITSU LIMITED

Purpose of SDEM® 2.0 Renewal

Chapter 1 What is SDEM?

1.1 Need for Standardization

1.2 Fujitsu Standardization

1.3 Incorporation of Global/De Facto Standards

1.4 History of Standardization at Fujitsu

Chapter 2 SDEM Structure

2.1 Processes

2.2 Categories

2.3 Phases

Chapter 3 Planning Process

3.1 Overall Flow

3.2 Categories

3.3 Phases

Chapter 4 Requirement Definition/Development/

Operational Test & Transition Process

4.1 Overall Flow

4.2 Categories

4.3 Phases

Chapter 5 Operation & Maintenance

Process

5.1 Overall Flow

5.2 Categories

5.3 Phases

Chapter 6 Contract/Organizational Management/System Audit Process

6.1 Contract Process

6.2 Organizational Management Process

6.3 System Audit Process

Chapter 7 Applying SDEM

Chapter 8 System Development Concepts Where "It is Natural for Existing Systems

to Exist"

8.1 Concept of New Development

8.2 Concept of Reconstruction

Conclusion

Appendix 1. File Structure

Appendix 2. Main Workflow of Requirement Definition Process (CA to RD Phases)

Appendix 3. Reconstruction Pattern

Appendix 4. Relationship Between Global/De Facto Standards and SDEM

Appendix 5. Details of SDEM 2.0 Changes

For internal

use

For internal

use * Parts of Chapter 4 and Appendix 5 are confidential information.

Therefore, the confidential information has been from the Standard Process Guide (FUJITSU-CONFIDENTIAL version) used by customers and partners.

● Explains SDEM concepts and application methods * Table of contents is below

Use if you:

- want to understand SDEM in more detail than

provided in this training course

- are a project manager who wants to understand

key points within the company to proceed

smoothly with projects

46

The SDEM Practical Standards provide more practical procedures and guides, document formats and

samples, etc., such as Business Application Development and System Infrastructure for each process and

category.

Use it to understand practical know-how about work you are in charge of or to determine the document

standards for a project.

Copyright 2022 FUJITSU LIMITED 47

4.3 Structure of SDEM Practical Standards

Copyright 2022 FUJITSU LIMITED

The SDEM Practical Standards provides specific work procedures, document formats,

etc. in practice.

* For the location of document formats and samples, including the SDEM Practical Standards, see "ドキュメントフォーマット・サンプル格納場所" (Document format/sample

storage location) on the following page:

https://fujitsu.sharepoint.com/sites/jp-IKB-sdem/SitePages/technology/sdeminformation.aspx

Use to:

- Understand practical know-how about work you

are in charge of

- Determine the document standards for a project

47

Chapter 5 explains how to apply SDEM to projects.

By the end of this chapter, you will understand the concept of applying SDEM to projects, the concept and

important points of tailoring, and the concept of utilizing SDEM in agile development.

Copyright 2022 FUJITSU LIMITED 48

5. Applying SDEM

Copyright 2022 FUJITSU LIMITED

What you will understand by the end of this chapter

- Concept of applying SDEM to projects

- Concept and important points of tailoring

- Concept of utilizing SDEM in agile development

48

The first is the concept of applying SDEM to projects.

SDEM is a comprehensive structure of work to be done in system construction. SDEM is not premised on a

specific product, system form, or implementation means.

Therefore, to apply it to an actual project, tailoring according to the project characteristics is necessary.

"Tailoring" means to customize the depth of WBS implementation according to project characteristics.

The viewpoints of tailoring include system characteristics, such as the scale and application type, and

conditions such as the development model, new development or reconstruction, skill level, and development

form.

Copyright 2022 FUJITSU LIMITED 49

5.1 Applying SDEM to Projects

Copyright 2022 FUJITSU LIMITED

SDEM is a comprehensive structure of work to be done in system construction. SDEM is not premised on a specific application

(scale or system form) or implementation means (process model, technique, tool).

Therefore, to apply it to an actual project, tailor (customize the depth of) and utilize the WBS implementation according to

the project characteristics.

Tailor and utilize according to project characteristics.

Project Characteristics

System

Characteristics

Technical

Conditions

Development

Conditions

- Scale

- Application type

- Core

system/Information

system

- Quality

requirements

etc.

- Development model

(Waterfall, agile,

etc.)

- New development,

reconstruction,

service application

- Methods/Tools

etc.

- Development

period

- Skills/Scheme

- Development

form

etc.

SDEM

Project standards

Tailoring

according to

project

characteristics

[Viewpoint of tailoring]

49

Here is an explanation of the concept of tailoring.

In many cases, you will refer to similar projects in the past to determine the project standards. The benefits

this will bring include a greater awareness of additional work due to project characteristics or optimization of

the formulation of the project standards. On the other hand, there is a risk that the work required for this

project will be omitted. Therefore, while referring to past projects, start tailoring based on all WBS of SDEM.

Especially for WBS1 and 2 level work, consider implementing every WBS once.

When deciding against implementation, it is important to be able to explain to a third party why the project

requirements can be met without the implementation. An example of a reason is that they are clearly not

applicable depending on the project scope.

A careless decision will lead to quality problems.

Depending on the development framework and applied language, for example, you may need to make a

choice or review the work at the WBS3 level.

There are special points to keep in mind when integrating or dividing a phase.

For example, depending on the project, the PS and PG phases are integrated in many cases.

However, as an example, do not integrate the RD phase of the requirement definition process and the UI

phase of the development process, or the ST phase of the development process and the OT phase of the

operational test & transition process.

The purposes of the phases differ greatly, so it is essential to judge the completion of each phase.

Conversely, it may be better to divide a phase.

For example, by dividing the IT phase into IT1, IT2, and IT3 depending on the scope of integration, you can

clarify the purpose to be achieved in each of them, and manage the quality, progress, etc. in divisions.

Copyright 2022 FUJITSU LIMITED 50

5.2 Concept of Tailoring

● WBS tailoring

Tailoring is implemented based on the following concepts.

⚫ Integrate and divide phases

Point 1. Do not integrate phases of different processes

As an example, do not integrate the RD phase of the requirement definition process and the UI phase of the development

process, or the ST phase of the development process and the OT phase of the operational test & transition process. The

purposes of the phases are different. Make sure the phases are independent of each other regardless of the period length.

Point 2. Divide a phase

If a phase has many system components (business, sub system, etc.) due to the project characteristics, divide the phase.

When dividing a phase and defining the sub phases, make it clear that the purpose of the original phase can be achieved, and

clarify the purpose and outline of each sub phase along with its name.

[Example of dividing the IT phase]

IT1 (Inter-program integration test within process), IT2 (Inter-process integration test), IT3 (Interface test with external system)

Copyright 2022 FUJITSU LIMITED

WBS1 Basically covers the implementation of all WBS

WBS2 Basically covers the implementation of all WBS

WBS3 Selects the WBS to be implemented according to project characteristics

Determines the depth of work to be done

50

51

This chapter ends with an explanation of how to use SDEM in agile development.

Agile development has no concept of dividing a phase. However, the fact remains that requirement

definition, design, implementation, and testing are agile actions.

The work and examination viewpoints defined in the SDEM WBS are the elements required for system

development.

Ascertain and utilize the required elements flexibly according to the purpose of development in the project.

Copyright 2022 FUJITSU LIMITED

5.3 Concept of Utilizing SDEM in Agile Development

The work and examination viewpoints defined in the SDEM WBS are the elements

required for system development.

Ascertain and utilize the required elements according to the purpose of development.

Copyright 2022 FUJITSU LIMITED

Planning/Research

Development Continuous development

Project first end  Respond to new issues Verify

...

Hypothesize

Design

Request

Test

Implement

Release

Verify

...

Verify

...

Operation/Maintenance Operation/Maintenance

Agile development has no concept of dividing a phase. The actions in each short

development cycle are requirement definition, design, implementation, and testing.

Check requests and repeat implementation in the short cycle to continuously create value.

Agile development

51

Chapter 6 explains specific SDEM usage scenarios.

By the end of this chapter, you will understand when to use SDEM, what can be done with SDEM, how far

the SDEM provision scope extends, and where to obtain SDEM.

Copyright 2022 FUJITSU LIMITED 52

6. SDEM Usage Scenarios

Copyright 2022 FUJITSU LIMITED

What you will understand by the end of this chapter

- When to use SDEM

- What can be done with SDEM

- How far the SDEM provision scope extends

- Where to obtain SDEM, and contact information

52

6.1 Use SDEM at These Times

● Project manager

Copyright 2022 FUJITSU LIMITED

Estimate costs

Plan scheme/role

division

Create master

schedule

⚫Extract the required work, and assume the work volume from the work description

⚫Plan a scheme by assuming the required skills from the categories corresponding to the

work, and divide the work

⚫Extract the work to be performed or approved by the customer, and the perceptions of both

parties are aligned beforehand

● Team leader (Business team, system infrastructure team, etc.)

Create detailed

schedule ⚫Extract all tasks in the team to create a schedule

● Team member

Implement initial

work ⚫Understand the procedure and viewpoints of the work

● Quality auditor in the organization

Create checklist ⚫Check if some checks were missed in the audit

What can be done with SDEM

Standard Process

Structure WBS Manual

Content used in relevant scenarios

WBS1-2-3 data

53

Here is an explanation of the typical usage scenarios of SDEM for each role.

The icons on the right represent the content mainly used in the scenario.

A project manager can use SDEM to estimate costs, create a master schedule, and plan a scheme and role

division.

All required work, including that related to the customer, can be extracted. This can be used not only for

planning Fujitsu's work but also for planning work where you need to share a common perception with the

customer early.

The next page explains an image of planning a scheme and role division using SDEM categories.

The leader of a business team, infrastructure team, or subsystem team can extract all the work in the team

by referring to specific WBS work to create a detailed schedule.

Team members will understand the procedure and viewpoints of the work even when experiencing the work

for the first time. They will also understand the positioning of their work in the overall work.

SDEM can be used not only in a project but also by quality auditors in the organization.

The auditors can check if they missed some checks on a checklist used in the audit.

Copyright 2022 FUJITSU LIMITED 53

Here is an explanation of an image of specific usage.

The figure on this page is an image showing SDEM usage for planning a project scheme and role division.

The SDEM categories are classified based on the relevance of knowledge and skills required for work. The

categories are used to clarify the targets such as application, infrastructure, and operations, and to define

the scheme and roles of the project.

As shown in the figure, confirm that all elements in the category, including the customer's scheme, are

assigned in order to prevent omissions and gaps in role division.

Copyright 2022 FUJITSU LIMITED 54

6.2 SDEM Usage Scenario 1) Planning Project Plan Scheme and Role

Division

Copyright 2022 FUJITSU LIMITED

[Example of development scheme planning]

A: Business management

T: Quality assurance

(Overall test)

B: Business

C: System requirements

D: Application

E: Application infrastructure

F: System infrastructure

G: Operation and maintenance

H: Transition & deployment

I: Development support

J: Project management

<Development process>

Project owner

Project manager

<Customer>

Business team

System infrastructure

team

Operation and

maintenance team

Transition and

deployment team

Project manager

Business team A Business team B

Application team A Application team B

Application

infrastructure team

<Fujitsu>

System infrastructure team

Operation and

maintenance team

Transition and

deployment team

Development

support team

Project owner

Use SDEM categories to clarify the targets (application, infrastructure, etc.)

and define roles for each group in the project.

Confirm that all elements in the category are assigned in order to prevent omissions

and gaps in role division.

54

55

Here is an explanation of another image of specific usage. This page explains a usage scenario for creating

a schedule.

First, extract the work and output required for the project from the SDEM WBS to create a schedule.

Then, you can assign and schedule all the deliverables you need to create.

Copyright 2022 FUJITSU LIMITED SDEM

A

B

C

D

E

.

J

VP SP CA . . OT OM

SDEMstandard

WBS

Collect required

work items

Collected Work Items

C4UI111 Screen transition design

C4UI112 Screen layout design

C4UI113 Screen item design

C4UI141 Collection of common

business messages

Work Item Document Person

-hours Personnel Schedule

Screen transition

design

Screen transition

diagram

10 A

Screen layout

design

Screen layout 7 B

Screen item

design

Screen item

definition

15 B

Collection of

common business

messages

Business

message list

30 C

I can create schedules

effectively without

omitting work items!

[New system project] Person-hour estimates/role division/schedule

Assign

deliverables and

personnel

New system

project leader

6.3 SDEM Usage Scenario 2) Creating Schedule

Define the project WBS based on the SDEM WBS, and create work items/schedules.

55 Copyright 2022 FUJITSU LIMITED

Here is an explanation of the scope of provision of SDEM 2.0.

SDEM is Fujitsu's core technology and important know-how for Fujitsu to outsource SI.

Therefore, provision to a customer or business partner is based on the premise that Fujitsu is entrusted with

SI.

In addition, a non-disclosure agreement, representing a confidentiality agreement, must be concluded.

As shown in the table, some content cannot be provided outside the company.

Furthermore, the scope of provision of the SDEM Practical Standards is determined by content.

When using it, check "利用上の注意事項" (Precautions for Use) on the IKB site.

Copyright 2022 FUJITSU LIMITED 56

6.4 Scope of SDEM 2.0 Provision

Copyright 2022 FUJITSU LIMITED

SDEM is copyrighted by Fujitsu, and the scope of provision varies depending on the content.

SDEM is Fujitsu's core technology and important know-how for Fujitsu to outsource SI.

Therefore, provision to an external party is based on the premise that an NDA is concluded and

Fujitsu is entrusted with SI.

SDEM Structure

Internal Provision

Scope External Provision Scope

Within

Company/Group

Business

Partner Customer

SDEM

Standard

Processes

Standard Process Structure ✓ ◆ ◆

WBS Manual ✓ ◆ ◆

Standard Process Guide

(FUJITSU-CONFIDENTIAL) ✓ ◆ ◆

Standard Process Guide

(for internal use)

✓ x x

WBS1-2-3 work item list

(CSV format)

✓ x x

[Legend]

✓: Can be provided

◆: Can be provided after the

conclusion of a non-disclosure

agreement (NDA), representing a

confidentiality agreement, on the

premise that Fujitsu is entrusted

with SI

x: Cannot be provided or shown

* For the provision scope of the SDEM Practical Standards, see "利用上の注意事項" (Precautions for Use) on the following page:

https://fujitsu.sharepoint.com/sites/jp-IKB-sdem/SitePages/technology/attention.aspx

56

⚫ A variety of information such as introductory materials and the content introduced in this training

course is available on the IKB-SDEM site.

6.5 SDEM 2.0 Published by IKB-SDEM

Copyright 2022 FUJITSU LIMITED

(IKB-SDEM site) https://fujitsu.sharepoint.com/sites/jp-IKB-sdem/SitePages/sdem.aspx

⚫ For inquiries, please contact us from [Inquiry] on the menu on the IKB-SDEM site.

* English versions of the

following content are

also available:

- SDEM Standard

Processes: Standard

Process Structure

- SDEM Practical Standards:

Operation and

Maintenance [ITSMOP]

57

The SDEM content introduced in this training course and the textbooks for this training can be obtained from

the IKB-SDEM site. Please make use of them.

For inquiries, please contact us from [Inquiry] on the menu.

The standard process structure "SDEM" is available to provide a system that our customers can use with

peace of mind. SDEM is the culmination of Fujitsu SE's wisdom and covers all system development tasks,

including the customer ones.

Please use SDEM to work with good quality and without omission.

Copyright 2022 FUJITSU LIMITED 57

Thank you

Copyright 2022 FUJITSU LIMITED

Copyright 2022 FUJITSU LIMITED 58