(Q FUJITSU-RESTRICTED )

FUJITSU

SDEM® 2.0

Getting Started 
Guide

.11111

Japan Global Gateway

[September 01, 2022]

Copyright 2022 FUJITSU LIMITED

This training course is intended for those who selected "SDEM 2.0 Getting Started Guide," for those not familiar with SDEM including the old SDEM, in the SDEM 2.0 Introductory Training.

Copyright 2022 FUJITSU LIMITED

1

(Q FUJITSU-RESTRICTED )

Contents	- SDEM Getting Started Guide	FUJITSU

1. What is SDEM?

1.1 Need for Standardization

1.2 Fujitsu Standardization 	= Standard Process Structure "SDEM"

1.3 Support for Global/De Facto Standards

1.4 History of Standardization at Fujitsu

2. SDEM Structure

2.1 SDEM Processes

2.2 Process Structure

2.3 Categories

2.4 Phases

2.5 WBS (Work Breakdown Structure)

(0 FUJITSU-RESTRICTED )	2	Copyright 2022 FUJITSU LIMITED

Copyright 2022 FUJITSU LIMITED

2

(Q FUJITSU-RESTRICTED )

Contents	- SDEM Getting Started Guide -	FUJITSU

3. Each SDEM Process

3.1 Planning Process

3.2 Requirement Definition/Development/Operational Test & Transition Process

3.2.1 Requirement Definition/Development/Operational Test & Transition Process Categories

3.2.2 Requirement Definition Process

3.2.3 Development Process

3.2.4 Operational Test & Transition Process

3.2.5 Main WBS Flow of Requirement Definition/Development/Operational Test & Transition Process

3.3 Operation & Maintenance Process

4. SDEM 2.0 Content Structure

4.1 Overall SDEM Structure

4.2 SDEM Standard Processes

4.3 Structure of SDEM Practical Standards

(0 FUJITSU-RESTRICTED )	3	Copyright 2022 FUJITSU LIMITED

Copyright 2022 FUJITSU LIMITED

3

(Q FUJITSU-RESTRICTED )

Contents	- SDEM Getting Started Guide	FUJITSU

5. Applying SDEM

5.1 Applying SDEM to Projects

5.2 Concept of Tailoring

5.3 Concept of Utilizing SDEM in Agile Development

6. SDEM Usage Scenarios

6.1 Use SDEM at These Times

6.2 SDEM Usage Scenario 1) Planning Project Plan Scheme and Role Division

6.3 SDEM Usage Scenario 2) Creating Schedule

6.4 Scope of SDEM 2.0 Provision

6.5 SDEM 2.0 Published by IKB-SDEM

(0 FUJITSU-RESTRICTED )	4	Copyright 2022 FUJITSU LIMITED

Copyright 2022 FUJITSU LIMITED

4

(Q FUJITSU-RESTRICTED )

## 1. What is SDEM?

Chapter 1 explains what SDEM is.

By the end of this chapter, you will understand why standardization is required in system development and what is SDEM, Fujitsu's standard processes.

Copyright 2022 FUJITSU LIMITED

5

(Q FUJITSU-RESTRICTED )

1.1 Need for Standardization - Why Standardization is Required - FUJITSU

To build quality, the processes for planning, design, implementation, 
	and testing must be done in the correct order.

To provide customers with systems they can use with peace of mind,

an architecture for work at the same quality bv many parties is required.

First is an explanation of why standardization is required in system development, operation, and maintenance.

To create high quality in systems, the processes for planning, design, implementation, and testing must be done in the correct order.

In addition, to provide customers with systems they can use with peace of mind, an architecture for work at the same quality by many parties is required.

The standardization of processes and the development architecture allows many parties to work at the same quality in the correct order.

Examples of standardization are:

- "standard processes" that define work contents and procedures, and

- "standard documents" that define the formats and rules of design, management, and other documents.

Copyright 2022 FUJITSU LIMITED

6

(Q FUJITSU-RESTRICTED )

1.1 Need for Standardization - Non-Standardized State -	FUJITSU

Quality varies depending on the person

V	✓

Work that should be done and descriptions in documents

are omitted

V	✓

Interfaces are incoherent and do not work well together

Maintainability is not good at the time of design change or repair after operation

(0 FUJITSU-RESTRICTED*)	7	Copyright 2022 FUJITSU LIMITED

So what kind of problems occur when processes and documents are not standardized?

For example, the following problems occur:

- Quality varies depending on the person

- Work that should be done is omitted

- Interfaces are incoherent and do not work well together

To prevent such problems, the required work and deliverables must be clarified. Standardization, that is, the processes and architecture in place, is important to ensure that the required work is carried out properly, even by those without experience.

Copyright 2022 FUJITSU LIMITED

7

(Q FUJITSU-RESTRICTED )

Various effects can be expected from standardization.

Firstly, when the documents created with the standard documents, the items written in them, and the required work are defined, you can prevent a dependence on the individual in work and quality.

Secondly, when the required work and its procedures are shown as standard processes, even inexperienced members can carry out manufacturing in the correct order.

Thirdly, when the role division and required work in standard processes are clarified, you can convey information accurately and without omission and unify how it is understood by the parties concerned.

Fourthly, after documents created using standard documents are handed over for operation and

maintenance, everyone understands what is written and where it is, which improves maintainability.

The next page explains what kind of standardization is underway at Fujitsu.

Copyright 2022 FUJITSU LIMITED

8

(Q FUJITSU-RESTRICTED )

1.2 Fujitsu Standardization = Standard Process Structure "SDEM'	FUJITSU

Fujitsu's standard process structure "SDEM"

- Systematizes the basic concepts and elements of planning,

development, operation and maintenance, and quality assurance activities in Fujitsu's system development as standard processes

- Comprehensively systematizes the who, what, when, and what order of 
	work to prevent omissions and ensure quality

- Gives a bird's-eye view of the whole like a map so that users 
	understand their positions in it and communicate in a common 
	language with the parties concerned

(0 FUJITSU-RESTRICTED )	9	Copyright 2022 FUJITSU LIMITED

Fujitsu's standard process structure is called "SDEM."

It shows the basic concepts of planning, development, operation and maintenance, and quality assurance activities for systems handled by Fujitsu.

It is a bible for comprehensively systematizing the who, what, when, and what order of work to prevent omissions and ensure quality.

By using SDEM, you can get a bird's-eye view of the whole like a map and understand your position in it. So you will be able to communicate in a common language with the parties concerned.

Copyright 2022 FUJITSU LIMITED

9

(Q FUJITSU-RESTRICTED )

1.3 Support for Global/De Facto Standards	FUJITSU

Systematization based on global/de facto standards such as ISO/IEC/JIS, Common 
	Frame, PMBOK, and ITIL, and Fujitsu's practical know-how

Various global standards 	Fujitsu's practical know-how

SDEM has been systematized by incorporating various domestic and global standards, such as Common Frame and ITIL, in addition to Fujitsu's conventional practical know-how.

As a result, it can be used for projects that require compliance with global standards.

Copyright 2022 FUJITSU LIMITED

10

(Q FUJITSU-RESTRICTED )

1.4 History of Standardization at Fujitsu	FUJITSU

Created in 1976, SDEM has more than 40 years of accumulated knowledge,

a compilation of Fujitsu's know-how, and is still evolving along with global trends.

System developmen 
	standards

SDEM®90

[Common Frame supported]

Standard process structure for solution-	Standard process structure for planning, development,

oriented planning, development,	operation, and maintenance

operation, and maintenance	Qnpiui®

SDEM®21

Planning	iration &	Operational

Standard process structure for planning, development, 
	operation, and maintenance

SDEM® 2.0

Contract process

process	intenance

process

Planning

process

"zz

Planning

Requirement 
	definition

P or

Organizational management process	Organizational management process

System audit process	System audit process

Organizational management process

System audit process

‘95 ISO 12207 (SLOP) 
	International standard for

software life cycle processes for bilateral contracts

‘96 PMBOK: International de facto standard for project management knowledge systems

irporat

management category

Since '03 - itSMF Japan (promotes ITSM in Japan)

Since'18- IPA

SEC BOOKS: User's Guide for Successful System Reconstruction

Points for Success in System Reconstruction

‘94 Common Frame 94 
	Japanese industry version for

SLOP

EExpanded work structuresxpanded work stru 
(contracts, qualit y y assurance, a: 
organizational i m mprovement, prc

Since ‘97 - Business expansion

(coinsulting and outsourcing), internalnsulting a 
	consultin'

focrmation changermation chi

- System development work divided 
	into 3 processes (planning, development,

operation & maintenance)

- New VP phase established, ME phase 
	renamed OM phase with operational

work added

Incorporated into operation &

maintenance process categories

Since ‘04 - IPA Software Engineering Center (SEC)

Quality assurance required by management 
strengthened planning process, independent 
requirement definition process, renamed

RD phase

Updated on premise that "it Is natural for existing systems to exist"

- Tacit knowledge from those experienced in 
	reconstruction, turned into explicit knowledge

reconstruction work process expanded and 
systematized

- WBS refined to match actual situations of 
	projects so that standards are more practical

(0 FUJITSU-RESTRICTED )	Copyright 2022 FUJITSU LIMITED

Fujitsu's SDEM has more than 40 years of accumulated knowledge, which continues to be used in the field as a compilation of Fujitsu's know-how.

Here is a brief explanation about its history.

SDEM was born in 1976.

The purposes were to break away from development practices that depend on individual skills, and to curb the ever-increasing development costs.

In 1995, SDEM supported the common framework established as an industry standard in Japan. At the time, not only system development but also contract and organizational work was added, creating a prototype for the current SDEM processes.

Since then, SDEM has continued to incorporate elements of international and de facto standards, responding to changes in the environment surrounding system construction.

In 2021, it was reformed into SDEM 2.0.

The main theme of SDEM up to then was "creating a new system." However, it is now commonplace to have an existing system.

Therefore, SDEM was updated on the premise that "it is natural for existing system to exist."

SDEM will continue to evolve in the future.

Copyright 2022 FUJITSU LIMITED

11

(Q FUJITSU-RESTRICTED )

FufiTSU

2. SDEM Structure

What you will understand by the end of this chapter

- What are SDEM categories, phases, and WBS

Copyright 2022 FUJITSU LIMITED

Chapter 2 explains the SDEM structure.

By the end of this chapter, you will understand the SDEM categories, phases, and WBS.

Copyright 2022 FUJITSU LIMITED

12

(Q FUJITSU-RESTRICTED )

First is an explanation of the SDEM process structure.

The SDEM processes are broadly divided into project processes and organizational processes.

The project processes consist of processes for the system life cycle and the contract process. The

processes for the system life cycle consist of five processes: planning, requirement definition, development, operational test & transition, and operation & maintenance.

The organizational processes are processes handled by the organization to support a project, and they consist of the organizational management process and system audit process.

This training course explains the processes from planning to operation & maintenance, which are related to the system life cycle.

For the contract, organizational management, and system audit processes, see the Standard Process Guide for SDEM 2.0.

Chapter 4 introduces the Standard Process Guide.

Copyright 2022 FUJITSU LIMITED

13

(Q FUJITSU-RESTRICTED )

2.2 Process Structure	FUJITSU

Systematization of "work to be done" along 2 axes: Vertical axis = Categories, Horizontal axis = Phases

Time axis

73

5

s

E.

Q.

o

CD

CQ

CD

IBBB	«,

(0 FUJITSU-RESTRICTED)	Copyright 2022 FUJITSU LIMITED

Here is an explanation of the structure of the SDEM processes.

The SDEM structure is a matrix with two axes: categories on the vertical axis, and phases on the horizontal axis.

The vertical axis shows the "required knowledge/skills" categories, and the horizontal axis shows the phases, which are the time axis.

"Work to be done" is defined at the intersection.

The vertical axis clarifies "who," the horizontal axis clarifies "when," and the intersection clarifies "what."

The subsequent pages explain the vertical axis "Categories" first, the horizontal axis "Phases" next, and "work to be done" finally.

Copyright 2022 FUJITSU LIMITED

14

(Q FUJITSU-RESTRICTED )

cP

2.3 Categories - Categories in Each Process -	FUJITSU

• Main categories of the work required to carry out each process

• Categories based on work relevance and the relevance of knowledge/skills required for work

Requirement definition process

Planning process

A: Business management

B: Business

C: System usage

D: System

E: Project management

(0 FUJITSU-RESTRICTED )

Development process

Operational test & transition process

A: Business management 
T: Quality assurance (Overall test) B: Business

C: System requirements D: Application

E: Application infrastructure F: System infrastructure

G: Operation and maintenance H: Transition & deployment

I: Development support 
J: Project management

15

Operation & maintenance process

A: Business management

B: Business

C: IT service management

D: System operation and 
	maintenance

E: Infrastructure provision

G: Project management

Copyright 2022 FUJITSU LIMITED

First is an explanation of the Categories vertical axis.

There are the main categories of work required to carry out each process. The categories are based on work relevance and the relevance of knowledge/skills required for work.

Therefore, they can be useful for teaming in a project, as an example.

The categories have been appropriately defined based on the characteristics of the planning process, the requirement definition, development, operational test & transition processes, and the operation & 
maintenance process.

Copyright 2022 FUJITSU LIMITED

15

(Q FUJITSU-RESTRICTED )

2.3 Categories - System as Combination of Many Technologies -	FUJITSU

A system is a combination of many technologies.

Important!

System does not work until it

A system is a "castle" 
	made up of many

technologies in a 
	stack.

(0 FUJITSU-RESTRICTED)

is all put together

Copyright 2022 FUJITSU LIMITED

Starting with this page, here is a further explanation of the categories in the requirement definition,

development, operational test & transition processes, which are the processes of system construction.

First of all, as a premise, a system is made up like this castle with many technologies in a stack. Be aware that an architecture for connecting and moving everything is important, and that the system does not work until it is all put together.

Copyright 2022 FUJITSU LIMITED

16

(Q FUJITSU-RESTRICTED )

The system structure corresponds to the categories in the requirement definition, development, and operational test & transition processes.

One category corresponds to "what customers want to achieve" and others correspond to "work required in system construction/operation" as roles required for system construction. There are other categories as well corresponding to parts of the system structure.

Each category is classified by adding an alphabet letter; for example, "A: Business management" and "B: Business."

Chapter 3 explains the contents of each category.

Copyright 2022 FUJITSU LIMITED

17

(Q FUJITSU-RESTRICTED )

2.4 Phases - Time Divisions in System Life Cycle -	FUJITSU

"Work to be done" by stakeholders involved in the system, mapped to the time axis of system construction Time period in the system life cycle, and unit for verifying a series of activities in system development

• Phases in each process

Time axis

Planning

process

Requirement

definition	Development process

process

Operational test Operation & 
	& transition 	maintenance

process	process

Main phase	Planning

Requirement 
	definition

Operational

Design	Implementation	Test	test and

transition

Operation and 
	maintenance

Operational 
	test and

transition

Operation and 
	maintenance

(0 FUJITSU-RESTRICTED)	Copyright 2022 FUJITSU LIMITED

Next is about the phases.

The SDEM phases are "work to be done" by stakeholders, such as our customers and us, and they are mapped to the time axis of system construction.

They are time divisions throughout the life cycle of such a system, from planning, requirement definition, design, implementation, test, and operational test and transition to operation and maintenance. They are also units for verifying the progress and quality of the work in system development.

Memorize the abbreviations at the bottom of this table because they are often used to represent the phases.

Copyright 2022 FUJITSU LIMITED

18

(Q FUJITSU-RESTRICTED )

2.4 Phases - V-shaped Model for Quality Assurance in System Development 	FUJITSU

• Entire development process

• Provide quality assurance by gradually decomposing and creating system components, and gradually integrating and verify them in 
	testing

• Match the system components at the requirement definition/design stage and the test stage, and verify and confirm quality with the 
	V-shape (V-shaped model for quality assurance)

Planning

Requirement 
	definition

Design	Implementation

Operational	Operation

T©St	test and	and

transition	maintenance

PS to PT

Evaluation by top management

i

w

•s

ST

3

System  ^

—V

Gradually

decompose 	Process

in requirement 
definition/design

Evaluation

Validation by users

Validation

Verification by designer

Verification

Verification by

-	develooers

Verification

*	«

Program

module

■ 	Enterprise

i

► Business

System

Gradually integrate 
in testing

|: System component

(0 FUJITSU-RESTRICTED)	Copyright 2022 FUJITSU LIMITED

Here is an explanation of how the entire development process is systematized.

In SDEM, as the requirement definition, design, and implementation phases progress, the target system

components are gradually refined and decomposed in the order of business, system, process, and program. In the test phase, the decomposed system components are integrated in the reverse order of process, 
system, and business for verification.

Then, those same components are matched and verified in opposing phases for quality assurance.

For example, in the ST phase test, verify that the system is as designed in the Ul phase. In the OT phase test, the user validates that the requirements defined for business in the RD phase are satisfied.

This is the concept of the V-shaped model for quality assurance.

Copyright 2022 FUJITSU LIMITED

19

(Q FUJITSU-RESTRICTED )

2.5 WBS (Work Breakdown Structure) - What is WBS? -	FUJITSU

Hierarchization of "work to be done" in 3 stages

WBS1 level	WBS2 level	WBS3 level

[Systematization] 
Most comprehensive 
project management

[Refinement]

Input units of development resources 
	Role units of project members

[Substantiation] 
Units of deliverables created

WBS code structure	Sub category*1 + phase*2 + serial number*3 + 00	Level-1 code + serial number*3 + 0	Level-2 code + serial number*3

Unit of standard filing for categories and phases	Unit that bundles documents for WBS2 level	Output for WBS3 level

File code structure	Level-1 code + f + serial number*3	Level-2 code + t + serial number*3	Level-3 code + d + serial number*3

C3UI100

Specification definition of

functional requirements (data)

1/

\

C3UI111 Definition of relationships between tables 
C3UI110

Database logical design	C3UI112 Development of logical table lists

C3UI113 Detailed design of logical tables

C3UI114 Index design

\it

*1 If no sub category, use "Main category + 1"

*2 If across phases/categories, use first phase/category

*3 1 to 9. Thereafter, A to Z

(0 FUJITSU-RESTRICTED)

C3UI120 
File logical design

<3

C3UI121 Development of file lists

C3UI122 Detailed design of files

Copyright 2022 FUJITSU LIMITED

Here is an explanation of WBS.

"WBS" stands for Work Breakdown Structure, which is the structure of "work to be done" for each phase and category.

SDEM hierarchizes it in three stages.

The WBS1 level is the systematization level, which provides an overall picture for comprehensive project management.

The WBS2 level is the refinement level, which refines the WBS1 work as the role units of project members. The work here is also a unit for drawing up a detailed project schedule.

The WBS3 level is a more specific version of work at the WBS2 level. Basically, the work here is a unit for creating deliverables.

The WBS of each layer is represented by assigned WBS codes indicating a category and phase.

Copyright 2022 FUJITSU LIMITED

20

(Q FUJITSU-RESTRICTED )

2.5 WBS - Extended WBS Across Categories -	FUJITSU

"Z" indicates work requiring consideration from an overall perspective across categories.

[List of CA phase work items (WBS1)]

In system development, some work needs consideration from an overall perspective across SDEM categories.

"Z" is used in the IDs of items requiring consideration across categories.

Example 1:

Z1CA200 Confirmation of reconstruction requests and

tentative definition of reconstruction pattern from requests perspective

Requiring consideration from an overall perspective across all categories

Example 2:

DZCA100 Overall understanding of current assets

Requiring consideration across sub categories in Category D

(0 FUJITSU-RESTRICTED)	Copyright 2022 FUJITSU LIMITED

In system development, some work needs consideration from an overall perspective across SDEM categories.

For that work, the letter "Z" is used in the category part of the WBS code.

Copyright 2022 FUJITSU LIMITED

21

(Q FUJITSU-RESTRICTED )

FuffTSU

3. Each SDEM Process

What you will understand by the end of this chapter

- Definition and workflow of every phase in each SDEM process

- Role of each category of the SDEM requirement

definition/development/operational test & transition process

Copyright 2022 FUJITSU LIMITED

Chapter 3 explains each SDEM process.

By the end of this chapter, you will understand the definition and workflow of each phase, and the role of each category.

Copyright 2022 FUJITSU LIMITED

22

(Q FUJITSU-RESTRICTED )

3.1 Planning Process

(0 FUJITSU-RESTRICTED )	23	Copyright 2022 FUJITSU LIMITED

Section 3.1 is about the planning process.

This section explains the definition and workflow of each phase.

Copyright 2022 FUJITSU LIMITED

23

(Q FUJITSU-RESTRICTED )

3.1 Planning Process - IT Vision Planning [VP] Phase -	FUJITSU

Investigate and analyze the current enterprise environment 
	and business to define IT vision goals and measures

Input information	Work item	Work item in next phase

Understand enterprise environment and business

■ Understand business policy and current business, 
	and extract issues

Understand enterprise environment, current business, 	Top management

Business

current system outline, restrictions, etc., and identify issues

I

Define IT vision

Plan IT system vision

- Define measures and initiative themes

- Systematize from IT system perspective, consider

feasibility and priority, and plan IT system vision

(0 FUJITSU-RESTRICTED)

personnel

System

planning

Top management 
	Business

personnel

Copyright 2022 FUJITSU LIMITED

The planning process includes the VP phase and SP phase. First, here is an explanation of the IT vision planning [VP] phase.

The purposes of the VP phase are to understand the current enterprise environment and business, and to clearly define the IT vision.

The VP phase defines measures and initiative themes based on the management policy and business policy, taking current issues into account.

Then, the overall consistency, feasibility, and priority are considered from the IT system perspective and summarized as the IT system vision.

Copyright 2022 FUJITSU LIMITED

24

(Q FUJITSU-RESTRICTED )

3.1 Planning Process - System Planning [SP] Phase -	FUJITSU

Based on the IT system vision, define new business requirements, estimate the ROI, and make decisions for system development

Work item in previous 
	phase

Work item

Define business requirements and system 
	requirement outline

Define business requirements and system requirement outline

- Take inventory of current system, and define new

Work item in next phase

Business

personnel

Define IT

vision

(0 FUJITSU-RESTRICTED)

business requirements and system requirement outline	Top management

- Formulate basic configuration plan for new system

\

Develop system plans

Develop system plans

- Estimate IT investment costs and verify ROI

- Develop overall system plan	Top management

- Develop project execution plan and pass it on to	Business

requirements definition process	personnel

Analyze curren 
	business and

system

Copyright 2022 FUJITSU LIMITED

Here is an explanation of the system planning [SP] phase.

The purposes of the SP phase are to clarify what kind of system should be constructed and to define new business requirements based on the IT system vision.

Agreement on the purpose and effects of the developed system is required of the parties concerned, in consideration of the market and technology trends.

The SP phase defines new business requirements and system outline requirements, determines the overall picture of the new system, and formulates a basic configuration plan for the new system. 
The costs are estimated, including the system development and operational costs of the next phase, and the ROI is verified based on the resulting estimates.

These are considered in the development of the overall system plan and project execution plan.

Copyright 2022 FUJITSU LIMITED

25

(Q FUJITSU-RESTRICTED )

In business transformation utilizing the latest digital technologies, that is, DX, IT human resources familiar

with digital technologies need to participate from the company-wide strategy planning and business strategy planning stages, not from the planning process.

Customers should play the main role in developing the company-wide strategy and business strategy.

However, as a DX partner, we should understand the customers' ideas and provide support as an IT expert.

Business & IT Grand Design Process Structure [BleDP] systematizes the work processes and knowledge for the DX vision/planning.

Since it is provided in the SDEM Technical Content, use it to support the customers' DX vision/planning. Chapter 4 introduces the SDEM Technical Content.

Copyright 2022 FUJITSU LIMITED

26

(Q FUJITSU-RESTRICTED )

3.2 Requirement Definition/Development/Operational Test & 
	Transition Process

(0 FUJITSU-RESTRICTED*)	27	Copyright 2022 FUJITSU LIMITED

Section 3.2 explains the requirement definition process, development process, and operational test &

transition process.

This section explains the roles of the categories, and then the definition and workflow of each phase.

Copyright 2022 FUJITSU LIMITED

27

(Q FUJITSU-RESTRICTED )

3.2.1 Requirement Definition/Development/Operational Test &

Transition Process Cateaories (1)

FUJITSU

Categories A and T correspond to "Overall control" and

Category B corresponds to "What customers want to achieve in business."

Main	Description	Sub Category

Category

A: Business management

T: Quality assurance 
	(Overall test)

A: Business	Judge the ROI, determine project	At: Business management

management startup, pause, transition, and	A2: Organization

completion, as well as organize and arrange organizations from the

viewpoint of business management.

C: System requirements D: Application

E: Application 
	infrastructure

F: System infrastructure

G: Operation and 
	maintenance

H: Transition & 
	deployment

I: Development support 
J: Project management

T: Quality	Promote overall test and manage

assurance	quality for the following purposes for

(Overall test)	production:

- Risk measures at project startup

- Early risk measures during the

project

Establish business specifications and perform business operational tests from the viewpoint of users.

- Substantiate business requirements, 
	and determine business

specifications that the customer will agree with.

- Design business operations, and 
	verify the operations as business.

T1: Business operation 
	continuity judgment criteria 
T2: Quality assurance

achievement level

T3: Quality assurance scenario T4: Overall test plan and

execution

T5: Individual test plan

B1: Business operation 
B2; Business function

B3: UX (Usage experience)

(0 FUJITSU-RESTRICTED)	Copyright 2022 FUJITSU LIMITED

Here is an explanation of the categories.

This page is about Categories A, T, and B. Categories A and T play the role of "Overall control" in system development, and Category B corresponds to "What customers want to achieve in business."

Category A is "Business management," which is to judge the ROI, determine the project startup, pause, transition, and completion, as well as organize and arrange organizations from the viewpoint of business management.

The customer's top management is in charge of this category because it should be done from the viewpoint of business management.

The sub categories subdivided from the main categories include "Business management" and "Organization."

Category T is "Quality assurance (Overall test)," which is to promote the overall test and manage quality for the following purposes for production: risk measures at project startup, and early risk measures during the project.

It is important to work on this category with the customer and vendors as an entire project.

The sub categories are "Business operation continuity judgment criteria," "Quality assurance achievement level," "Quality assurance scenario," "Overall test plan and execution," and "Individual test plan."

Category B is "Business," which is to establish business specifications and perform business operational tests from the viewpoint of users. This category determine the specific business the customers want to achieve.

The sub categories are "Business operation," "Business function," and "UX (Usage experience)."

Copyright 2022 FUJITSU LIMITED

28

(Q FUJITSU-RESTRICTED )

3.2.1 Requirement Definition/Development/Operational Test &

Transition Process Cateaories (2

FUJITSU

Category C corresponds to "Architecture for connecting and moving everything" and

Categories D, E, and F correspond to the system structure from applications to infrastructures.

Main	Description	Sub Category

Category

C: System	Design the overall system

requirements architecture for doing business 
	and then pass on that

information to each category.

D: Application	Design, develop, and test

applications (including packages).

C1: Overall system architecture 
C2: Functional requirements (System

functions)

C3: Functional requirements (Data) 
C4: Functional requirements (Interface) 
C5: Non-functional requirements 
C6; Security

D1: New application development and 
	diversion development

D2: Package usage 
D3: Migration (Source code conversion)

E: Application	Design and provide common	E1: Application architectures (including

infrastructure	application functions deployed	frameworks)

as a common infrastructure.	E2: Database architectures and

definitions (Applications)

E3: Application environment

F: System	Design and provide the system

infrastructure	configuration and environment,

network, databases, and system operations that are required for 
system implementation.

FI: Performance & scalability F2: Reliability

F3: Security

F4; External connectivity

F5: System configuration & environment F6: Database

F7: Network 
F8: Facility

F9: System operation

(0 FUJITSU-RESTRICTED)	Copyright 2022 FUJITSU LIMITED

Here is an explanation of Categories C to F. Category C corresponds to the architecture for connecting and moving everything, and Categories D, E, and F correspond to the system structure from application to 
infrastructure.

Category C is "System requirements," which is to design the overall system architecture for doing business and then pass on that information to each category.

The sub categories are "Overall system architecture," "Functional requirements (System functions),"

"Functional requirements (Data)," "Functional requirements (Interface)," "Non-functional requirements," and "Security."

Category D is "Application," which is to design, develop, and test applications.

The sub categories are "New application development and diversion development," "Package usage," and "Migration (Source code conversion)'' depending on the application development method.

Category E is "Application infrastructure," which is to design and provide common application functions deployed as a common infrastructure.

The sub categories are "Application architectures (including frameworks)," "Database architectures and definitions (Applications)," and "Application environment."

Category F is "System infrastructure," which is to design and provide the system configuration and

environment, network, databases, and system operations that are required for system implementation. Category F also includes the infrastructure, OS, middleware, and operational infrastructure. 
The sub categories are classified by elements for meeting non-functional requirements. They include "Performance & scalability," "Reliability," "Security," "External connectivity," "System configuration & environment," "Database," "Network," "Facility," and "System operation."

Copyright 2022 FUJITSU LIMITED

29

(Q FUJITSU-RESTRICTED )

3.2.1 Requirement Definition/Development/Operational Test &

Transition Process Cateoories (3)

FUJITSU

Category G corresponds to "Post-production preparation" and

Categories H, I, and J correspond to "Work required in system construction/operation."

Main Category |	Description	Sub Category

G: Operation and Prepare for operation and	G1: Operation & maintenance

maintenance maintenance after production

(transition, etc.).

H; Transition &	Plan and design transition and	H1; Transition plan

deployment	deployment, and perform transition	H2: Business system transition

rehearsal and the actual transition.	H3; Data transition

H4: Deployment

I: Development	Establish development standards for	11: Development standard

support	overall project integration, and	I2: Configuration management

develop and operate a framework for

configuration management, tools,

J: Project	Develop project plans and establish	J1: Integration management

management	project goals (deadline, quality, cost,	J2: Scope management (Requirement

etc.) for production, and promote and	management)

operate the project.	J3: Time management (Progress management)

J4: Cost management (Profit and loss 
	management)

J5: Quality management (Quality and defects 
	management)

J6: Human resource management (Personnel 
	management)

J7: Communications management (Information 
	distribution and performance report) 
J8: Risk management (Risk control) 
J9: Procurement management (External 
	procurement management)

JA: Contract management (Contracts with 
	customers)

JB: OSS application management

(0 FUJITSU-RESTRICTED)	30	Copyright 2022 FUJITSU LIMITED

Last is Categories G to J.

Category G corresponds to "Post-production preparation." Categories H, I, and J correspond to "Work required in system construction/operation."

Category G is "Operation and maintenance," which is to prepare for operation and maintenance after production. The only sub category is "Operation & maintenance."

Category H is "Transition & deployment," which is to plan and design transition and deployment, and perform transition rehearsal and the actual transition.

The sub categories are "Transition plan," "Business system transition," "Data transition," and "Deployment."

Category I is "Development support," which is to provide support for smooth development practice, establish development standards for overall project integration, and develop and operate a framework for 
configuration management, tools, etc.

The sub categories are "Development standard" and "Configuration management."

Category J is "Project management," which is to develop project plans and establish goals such as deadline, quality, and cost for production, and promote and operate the project.

There are eleven sub categories in total. "Integration management," "Scope management (Requirement management)," "Time management (Progress management)," "Cost management (Profit and loss 
management)," "Quality management (Quality and defects management)," "Human resource management (Personnel management)," "Communications management (Information distribution and performance 
report)," "Risk management (Risk control)," and "Procurement management (External procurement 
management)" correspond to the knowledge area in the PMBOK 6th Edition. "Contract management 
(Contracts with customers)" and "OSS application management" are unique to SDEM.

Copyright 2022 FUJITSU LIMITED

30

(Q FUJITSU-RESTRICTED )

3.2.2 Requirement Definition Process - Current Business and System	fi hitch

Analvsis FCA1 Phase -	'

Analyze the current situation, determine the development method, and reach an

agreement with stakeholders on risk

Work item in previous phase

• Purposes of the CA phase

1. Determine if the requirement definition or 
	development phase can begin, and make

up for any missing information

Work item

Current analysis

i Analyze current business and system

Analyze current business, system, operations

Business 
Application

Work item in next phase

Define business 
	and system

requirements 
(Reconstruction +

2. Determine the reconstruction pattern and 
	eliminate any discrepancy in awareness

between the customer and us

3. Reach an agreement with the customer 
	about possible risks in the previous

phase and ideas on hedging the risks

Define

business

requirements

Define system 
	requirement

outline

Application infrastructure V	ew)

and incompatibilities

System infrastructure 
	Personnel

Agree on reconstruction pattern*/risk

Determine

I Agree on reconstruction pattern/risk	reconstruction

- Evaluate feasibility and determine reconstruction pattern based	pattern with new

requirements

on investigation results	Top management

- Reach agreement with stakeholders on risk	Project manager

Formulate quality assurance scenario

► (Continues to RD phase)

i Formulate quality assurance scenario

Develop	Formulate business operation continuity judgment criteria	Top management

system plans	and quality assurance achievement levels	Business personnel

Project manager

* Reconstruction pattern: Reconstruction method such as rehost, rewrite, and rebuild

(0 FUJITSU-RESTRICTED)	31	Copyright 2022 FUJITSU LIMITED

Each phase will be explained. First, the requirement definition process phase.

The requirement definition process includes the CA and RD phases. This page explains the current business and system analysis [CA] phase.

The CA phase has three purposes.

The first is to determine if the requirement definition or development phase can begin, and make up for any missing information.

The second is to determine the reconstruction pattern and eliminate any discrepancy in awareness between the customer and us.

The third is to reach an agreement with the customer on possible risks in the previous phase and ideas on hedging the risks.

In order to realize these purposes, analyze the current business, system, operations, and incompatibilities, and evaluate the feasibility and determine the reconstruction pattern based on the investigation results. Next, reach an agreement with the customer on risk.

In addition, for quality assurance after production, formulate the business operation continuity judgment criteria and the quality assurance achievement levels.

Note that the reconstruction pattern means the reconstruction method such as rehost, rewrite, and rebuild.

Copyright 2022 FUJITSU LIMITED

31

(Q FUJITSU-RESTRICTED )

3.2.2 Requirement Definition Process - System Requirement Definition	_..o° ..

[RD1 Phase-	i-ujilbu

Define requirements and design the overall architecture, which are required for system 
	implementation, and reach an agreement with stakeholders

Work item in previous phase

Analyze

current

business and 
	system

Agree on 
reconstruction

Work item

Define business requirements (Reconstruction + New) 
	■ Define business requirements

Define requirements for business operations and functions

Define system requirements (Reconstruction + New)

■ Define functional requirements

Define requirements for system functions, data, and interfaces

Define non-functional requirements 	Business _

Define requirements for performance, scalability, reliability, 	Application

Security, etc. 	infrastructure

Work item in next phase

Design business 
	and system

specifications

Design

architecture

Design 
configuration

pattern/risk

rFormulate quality^

Define overall architecture requirements

Define overall system architecture requirements

System infrastructure

Personnel

Design 
operations

assurance

scenario

'H

Determine reconstruction pattern with new requirements

Top management 
	Project manager

(Continued from CA phase)	►

(0 FUJITSU-RESTRICTED^

Formulate quality assurance scenario/overall test plan

Copyright 2022 FUJITSU LIMITED

Here is an explanation of the system requirement definition [RD] phase.

The purposes of the RD phase are to define requirements and design the overall architecture, which are required for system implementation, and reach an agreement with stakeholders.

Define the requirements for business operations and functions, integrating reconstruction requirements and new requirements. System requirement definition is divided into functional requirements and non-functional requirements. The functional requirements include those for system functions, data, and interfaces. The non-functional requirements include those for performance and scalability, reliability, and security. In 
addition, define the requirements for the overall system architecture.

Finally, confirm the reconstruction pattern determined in the CA phase, formulate the quality assurance scenario and overall test plan, and reach an agreement with stakeholders on requirement definition.

Copyright 2022 FUJITSU LIMITED

32

(Q FUJITSU-RESTRICTED )

3.2.3 Development Process - User Interface Design [Ul] Phase - FUJITSU

Design external system specifications from the user perspective, design the architecture for system 
	implementation, and reach an agreement with stakeholders

Work item in previous phase

Work item

Design business and system specifications

■ Define functional requirement specifications

Substantiate specifications of system functions, data,

Work item in next phase

Application^^	Design

Application^^"^	structure

infrastructure

Define business and 
system requirements

(Reconstruction +

New)

and interfaces

Design architecture

■ Design application architecture

Substantiate processing methods such as screen control, transition, and batch start mode

Design configuration

Design architecture/system configuration for performance, reliability, etc.

- Determine implementation methods for performance, 
	scalability, reliability, etc.

System infrastructure 
	personnel

Set up

Application "	application

Application	infrastructure

infrastructure 
	personnel

Design

system	environment

infrastructure 
	personnel

- Determine configurations of hardware, software, databases, etc., 
	and network methods

Design operations	(Continues to SS phase)

(0 FUJITSU-RESTRICTED)	33	Copyright 2022 FUJITSU LIMITED

The explanations from here cover the phases of the development process. The development process includes the phases from Ul to ST.

First is an explanation of the user interface design [Ul] phase.

The purposes of the Ul phase are to design external system specifications from the user perspective, design the architecture for system implementation, and reach an agreement with stakeholders.

In designing business and system specifications, substantiate the system functions, data, interfaces, screens, and forms based on the requirement definition of the RD phase.

In addition, design the application architecture, design an architecture for ensuring performance, reliability, etc., and determine the configurations of hardware, software, databases, etc.

Furthermore, as operation design, design the operation methods, etc. for stable, abnormal, or maintenance operations.

Copyright 2022 FUJITSU LIMITED

33

(Q FUJITSU-RESTRICTED )

3.2.3 Development Process - System Structure Design [SS] Phase -	FUJITSU

Design for system implementation, and confirm that the user interface design 
	reflects the specifications agreed upon

Work item in previous phase

Design business 
	and system

specifications

Design

architecture

Design

Work item

Design structure

Design application structure

- Divide process into programs in functional units

- Define program function outline

Set up application infrastructure

■ Develop application infrastructure programs

Develop application infrastructure programs (Programming, program test)

Design environment

i Design system environment, database, etc.

Work item in next phase

Application 
	personnel

Implement

_

Application

infrastructure 
	personnel

Set up 
environment

configuration	- Design system environment such as hardware and software System

infrastructure

- Develop physical and environmental designs of databases "* 	*'

Design

operations

(Continued from the Ul phase)

(0 FUJITSU-RESTRICTED^

and design network environment

Design operations

personnel

Copyright 2022 FUJITSU LIMITED

Here is an explanation of the system structure design [SS] phase.

The purpose of the SS phase is to design for system implementation. In so doing, develop the design agreed upon with the stakeholders.

The design for implementation in this phase is based on the business and system specifications, architecture design, configuration design, and operation design in the Ul phase.

In designing the application structure, define the program divisions and functions.

In setting up the application infrastructure, create application infrastructure programs one stage earlier than the start of business programming.

Then, in designing the environment, develop the environment design such as parameters related to

hardware and software installed in the system, develop the physical design of the databases, and so on.

Copyright 2022 FUJITSU LIMITED

34

(Q FUJITSU-RESTRICTED )

3.2.3 Development Process - Implementation Phase [PS to PT] (1) -	FUJITSU

Create programs and ensure quality by verifying them in program units

Work item in previous phase

Design

structure

Set up

application 
infrastructure

Work item

Implement

■Design	■Do

program	programming

structure	Perform coding,

Develop structural	etc. designs, such as

module division, and detailed

designs

■ Develop integration test specifications

Develop integration test specifications

Work item in next phase

■Test programs

Run tests on 
programs

Run

integration test

Application 
	personnel

PS phase \ PG phase \	PT phase

(0 FUJITSU-RESTRICTED)	Copyright 2022 FUJITSU LIMITED

This and the next page explain the program structure design [PS] phase, programming [PG] phase, and program test [PT] phase collectively as the implementation phase.

First is an explanation of application-related work.

The PS phase develops program structure designs, such as module division, and the detailed designs of logic and algorithms to definitely incorporate the design results of the 55 phase into programs. 
The PG phase performs program coding.

The PT phase verifies the programs implemented in program units and ensures quality.

Copyright 2022 FUJITSU LIMITED

35

(Q FUJITSU-RESTRICTED )

3.2.3 Development Process - Implementation Phase [PS to PT] (2) -	FUJITSU

Work item in previous phase

Design

environment

Design

operations

System

Work item

Set up environment

■Install hardware and software, 
	and check operations

- Install hardware and software, and 
	configure their environment

- Develop system infrastructure test

specifications

■Install database, etc.

- install and configure database

Work item in next phase

Test system 
infrastructure

■Test system 
	infrastructure

[Up to IT]

Run tests on	>► (Continues to test phase)

system

infrastructure^

System

infrastructure	infrastructi

personnel	environment, network devices, etc.	personne

Develop system infrastructure test

specifications

PS phase	PG phase	PT phase

(0 FUJITSU-RESTRICTED )	36	Copyright 2022 FUJITSU LIMITED

Here is an explanation of the system infrastructure work.

Set up the environment during the PS phase to PG phase.

Install hardware and software, set parameters, and install and configure the database environment, network devices, etc.

In the PT phase, test the environment that has been set up. Run the system infrastructure test by the first half of the IT phase.

Copyright 2022 FUJITSU LIMITED

36

(Q FUJITSU-RESTRICTED )

3.2.3 Development Process - Test Phase [IT to ST] -	FUJITSU

Verify the quality of integrated functions and interfaces between functions [IT]

Verify the overall system quality, and confirm the achievement of the quality assurance 
	achievement levels [ST]

Work item in 
previous phase

Integration test

■Integration test

Implement	Test functions of	“

business

applications overall H

Application 
	personnel

System infrastructure 
	test

■System

Work item

Integration test 
(Business and

infrastructure 
	integration)

■Integration test

Integrate business 
applications and 
infrastructure, and 
test interfaces A

System test

■System test

Run test

appropriate to

business operations Verify overall

system

- Functionality	A

- Non-functionality^^

(Performance,

Work item in next

Run

operational 
	test

(Continued from ■ 
implementation 
phase)

infrastructure test	“

[PT and later]

Test system	System

infrastructure	infrastructure

personnel

Application 
	Application 
infrastructure

System

infrastructure 
	personnel

scalability,	Application 
reliability, etc.) Application

- Operation	infr“*™^ure

infrastructure 
	personnel

IT phase	y	ST phase

(0 FUJITSU-RESTRICTED)	Copyright 2022 FUJITSU LIMITED

This page explains the integration test [IT] phase and system test [ST] phase collectively as the test phase.

The purposes of the IT phase are to integrate programs whose quality was confirmed in the PT phase, and to verify the quality of integrated functions and interfaces between functions.

First, run the integration test for the business applications overall.

Next, after the system infrastructure test is completed, run the integration test for the business applications on the system infrastructure. Also, verify interface quality by integrating the business and infrastructure.

The purposes of the ST phase are to verify the overall system quality and to confirm the achievement of the quality assurance achievement levels formulated together with the customer.

In the system test, verify the overall system from functional aspects, non-functional aspects such as

performance and reliability, and operational aspects. For the test, use the data and system environment appropriate to the actual business operations if possible.

Copyright 2022 FUJITSU LIMITED

37

(Q FUJITSU-RESTRICTED )

3.2.4 Operational Test & Transition Process - Operational Test and 
	Transition TOTl Phase -

FUJITSU

Make production decisions based on a business scenario verification and business operation continuity judgment to transition to the new system

Work item in previous phase

Operational test

Operational test 
and transition to 
new business

System test	- Users become familiar

with system and 
understand problems 
in business operations

- Switch from current

Work item

Transition decision	Transition and

making	deployment

■ Transition	■ Transition

decision	Perform

making	transition of

system and data Evaluate whether

quality goal was 
achieved, and 	d

make decision on	Deployment

transition	Deploy

'Pr

l

Transition and

business to new	deployment

business	management	personnel

(0 FUJITSU-RESTRICTED)	Copyright 2022 FUJITSU LIMITED

This page explains the operational test & transition process phase. The phase is operational test and transition [OT].

The purposes of the OT phase are to make a business operation continuity judgment based on business scenario verification results, etc., make production decisions based on that, and transition to the new system.

As the operational test, users verify the business scenario. Based on the business operation continuity

judgment criteria and production agreed upon with the customer, determine if production is possible and if transition to the new system is possible.

When there is no problem, perform transition and deployment of the system and data.

Copyright 2022 FUJITSU LIMITED

38

(Q FUJITSU-RESTRICTED )

The explanations so far have covered the roles of categories of the SDEM requirement definition,

development, operational test & transition processes, and the definition and workflow of each of their phases.

This diagram shows the main workflow in requirement definition, development, operational test & transition.

The explanations so far have mainly covered construction work and quality assurance. In addition to that, preparation for operation and maintenance after production, work for transition and deployment, 
development support, project management, and various other work have been defined.

Copyright 2022 FUJITSU LIMITED

39

(Q FUJITSU-RESTRICTED )

3.3 Operation & Maintenance Process

(0 FUJITSU-RESTRICTED*)	40	Copyright 2022 FUJITSU LIMITED

Section 3.3 explains the operation & maintenance process.

Copyright 2022 FUJITSU LIMITED

40

(Q FUJITSU-RESTRICTED )

3.3 Operation & Maintenance Process - Operation and Maintenance 	FUJITSU

Develop a plan for safe and stable operation of the IT system, and regularly 
	review and improve the plan

A: Business management (Business management, organization) 
	B: Business (Business operation)

C1: Integrated management (Operation and maintenance management, business continuity planning, etc.)

* A: Business management,

B; Business, 
Cl; Integrated

management, etc. are categories.

C

cS

JR

X

0

D1: Business operation

(Business monitoring, business troubleshooting, business operation document management, etc.)

C2: Operational management

Service desk, incident management, 
TP problem management, operational

improvement, etc.)

D2: System operation

(System monitoring, system 
troubleshooting, system operation 
document management, etc.)

D3: Application maintenance

(Application failure support, application modification/specification change, data maintenance, etc.)

D4: Infrastructure maintenance

(Hardware failure support, software 
failure support, network failure support, 
database environment change, etc.)

E1: Infrastructure provision (Facility provision/management, IT resource provision, etc.)

G: Project menagement (Scope management, time management, cost management, etc.)

(0 FUJITSU-RESTRICTED^	41	Copyright 2022 FUJITSU LIMITED

The operation & maintenance process includes only the operation and maintenance [CM] phase because it has no concept of start and end like in a development project.

In the OM phase, develop a plan for safe and stable operation of the system, and regularly review and improve the plan cyclically.

For daily operation and maintenance, go through a cycle centered on operation management, from business operation, system operation, application maintenance, and infrastructure maintenance request to delivery. Engage in integrated management from the perspective of management and business.

Copyright 2022 FUJITSU LIMITED

41

(Q FUJITSU-RESTRICTED )

Fujfrsu

4. SDEM 2.0 Content Structure

What you will understand by the end of this chapter

- What kind of content is provided with SDEM

- Types of SDEM practical standards, and what is provided

Copyright 2022 FUJITSU LIMITED

Chapter 4 explains the SDEM content structure.

By the end of this chapter, you will understand the content provided with SDEM, types of SDEM practical standards, which are part of it, and what is provided.

Copyright 2022 FUJITSU LIMITED

42

(Q FUJITSU-RESTRICTED )

4.1 Overall SDEM Structure

SDEM Standard Processes

Structure of standard processes showing the basic concepts of planning, development, operation and maintenance, and quality assurance activities at Fujitsu

WBS1 Structure

■

WBS2 Structure

Standard Process Guide	WBS Manual

Describes concepts of using	Defines work items and

deliverables of WBS3 units, and

FUJITSU

SDEM Practical Standards

Specific work procedures, document formats, etc. for practical use

SDEM and construction

explains key points on work

[ITReSP]	[ITCMAP]

Reconstruction	Common

Planning	Development

Current Anal

[ITUMAP]	Item List

UX Design

[ITBASP]	[III MAP]

Business 
	Application 
Development

Security,	Performance,

Extended	Extended

Reliability, 
Extended

[ITSMOP] 
Operation and

Maintenance

[ITBAMR]

Business 
Application 
Modification

SDEM Technical Content

Know-how, document samples, etc. useful in practice

Agile Practical Work Model

Migration Project 
Work Standard WBS

Business & IT Grand Design 
	Process Structure (BleDP)

(0 FUJITSU-RESTRICTED)

Tri-shaping	Secure Web Guide

Important Security

Estimation Guidelines	Requirements for Customers’

Internet-connected Systems

Past FCP Community Knowledge

Risk Measure Standards for

Using Open Source Software

OSS Usage Guide

Copyright 2022 FUJITSU LIMITED

SDEM broadly consists of the SDEM Standard Processes, the SDEM Practical Standards, and the SDEM Technical Content.

The SDEM Standard Processes are a general-purpose work structure independent of industry, language, development environment, and so on. It covers the overall work required for planning, development, 
operation and maintenance, and quality assurance activities.

They contain three types of content: Standard Process Structure, WBS Manual, and Standard Process Guide.

The SDEM Practical Standards are provided as more practical work standards for each field. Document formats, samples, specific work procedures, and guides are provided.

The SDEM Technical Content contains technical know-how and document samples useful in practicing Fujitsu project work.

Starting with the next page, the content provided in the SDEM Standard Processes is introduced.

Copyright 2022 FUJITSU LIMITED

43

(Q FUJITSU-RESTRICTED )

4.2 SDEM Standard Processes - Standard Process Structure	FUJITSU

• SDEM (WBS1-2 structure) key point summary

[Planning, requirement definition, development, operational test &

transition, operation & maintenance process WBS11

-'A'- Use for project planning (estimation, schedule creation, role 
	V division), etc.

[Explanation of categories and phases]

• WBS1-2 provided

• Printable (A3) files also provided

• WBS data in CSV format also provided	Use to;

(WBS1-2-3)	V - Collect detailed tasks

- Extract the WBS name in schedule creation

(0 FUJITSU-RESTRICTED*)	Copyright 2022 FUJITSU LIMITED

First is an explanation of the Standard Process Structure.

This content includes the WBS1 and WBS2 structures, categories, and phase definitions of the SDEM standard processes.

Take advantage of the content to get an overall picture of the SDEM standard processes.

When estimating project work and planning role division, be sure to use this standard process structure.

In addition, WBS1, WBS2, and WBS3 lists are provided in CSV format. Use them for project standardization, WBS name extraction in schedule creation, etc.

Copyright 2022 FUJITSU LIMITED

44

(Q FUJITSU-RESTRICTED )

4.2 SDEM Standard Processes - WBS Manual -	FUJITSU

• Explanation of key points of work in each WBS

SDEM2.0 WBSKIfl®

m : C/7.TASW5EH	• Provided in WBS2 units

• Describes the WBS purpose and input/output

WB 5911 U'VU

• Describes key points of work and viewpoints for

WBB1H2U^/U	6280110

& vX-ri.BTrWft'7 r <

|	|&2BD?0Qfl	jjgftgwFtKajfrT

WBSH3
«H*& ts*. $ 5 	« H 7 □ -b x 	• OA l' li L

ar

tf

11 Esift

aa	F

consideration for WBS3 individually

* The WBS Manual is not provided for Categories C 
	to E in the operation & maintenance process

(OM).

See the SDEM Practical Standards: Operation and 
	Maintenance (ITSMOP).

Use to:

Hi aa u * ® * r ? p -t *	* n <nm at < t	« s saa e ftiMKtt-ojK*?!'

' it »-««*•*)

»SHS3S«mja«y	II !.««*#)

<*a>

DtUttSL. »tt»*£l«il1hr4:

- Understand the procedure and viewpoints of 
	work you are in charge of

- Get reviewers and auditors to check if they 
	missed some checks

(0 FUJITSU-RESTRICTED )	45	Copyright 2022 FUJITSU LIMITED

Next is about the WBS Manual in the SDEM Standard Processes.

This content is provided in WBS2 units.

It shows what to input or output in each WBS, and the key points of work and viewpoints for consideration for WBS3 individually.

Use it to understand work you are experiencing for the first time, and so on.

This content also includes the WBS purpose.

When performing work, it is important to understand the purpose of the work.

When reading the 1W6S Manual, pay attention to this purpose to deepen your understanding.

Copyright 2022 FUJITSU LIMITED

45

(Q FUJITSU-RESTRICTED )

4.2 SDEM Standard Processes - Standard Process Guide -	FUJITSU

• Explains SDEM concepts and application methods	* Table of contents is below

Use if you:

Purpose of SDEM® 2.0 Renewal

Chapter 1 What is SDEM?

1.1 Need for Standardization

1.2 Fujitsu Standardization

1.3 Incorporation of Global/De Facto Standards

Chapter 5 Operation & Maintenance 
	Process

5.1 Overall Flow

5.2 Categories

5.3 Phases

V - want to understand SDEM in more detail than 
	provided in this training course

- are a project manager who wants to understand 
	key points within the company to proceed

smoothly with projects

1.4 History of Standardization at Fujitsu

Chapter 2 SDEM Structure

2.1 Processes

2.2 Categories

2.3 Phases

Chapter 3 Planning Process

3.1 Overall Flow

3.2 Categories

3.3 Phases

Chapter 4 Requirement Definition/Development/ 
	Operational Test & Transition Process!

4.1 Overall Flow

4.2 Categories

4.3 Phases

Parts of Chapter 4 and Appendix 5 are confidential information.

Chapter 6 Contract/Organizational Management/System Audit Process 
	6.1 Contract Process

6.2 Organizational Management Process

6.3 System Audit Process

Chapter? Applying SDEM

Chapter 8 System Development Concepts Where "It is Natural for Existing Systems 
	to Exist"

8.1 Concept of New Development

8.2 Concept of Reconstruction

Conclusion

Appendix 1. File Structure

Appendix 2. Main Workflow of Requirement Definition Process (CA to RD Phases) Appendix 3. Reconstruction Pattern

Appendix 4. Relationship Between Global/De Facto Standards and SDEM Appendix 5. Details of SDEM 2.0 Changes |~'

Therefore, the confidential information has been from the Standard Process Guide (FUJITSU-CONFIDENTIAL version) used by customers and partners.

(0 FUJITSU-RESTRICTED)	46	Copyright 2022 FUJITSU LIMITED

The third type of content in the SDEM Standard Processes is the Standard Process Guide. This page shows the table of contents of the guide.

This content explains each SDEM process and the concepts of SDEM application methods.

The Standard Process Guide has been divided into an internal version and the FUJITSU-CONFIDENTIAL version. The internal version explains the key points to progressing smoothly in a project. 
Read it if you want to understand these points or want to understand SDEM in more detail than provided in this training course.

These pages have explained the Standard Process Structure, WBS Manual, and Standard Process Guide in the SDEM Standard Processes.

Next is an explanation of the SDEM Practical Standards.

Copyright 2022 FUJITSU LIMITED

46

(Q FUJITSU-RESTRICTED )

4.3 Structure of SDEM Practical Standards	FUJITSU

The SDEM Practical Standards provides specific work procedures, document formats,	vf - Understand practical know-how about work you

etc. in practice.	are in charae of

- Determine the document standards for a project

*1 The Business & IT Grand Design Process Structure (BleDP) is available in the SDEM Technical Content.

* For the location of document formats and samples, including the SDEM Practical Standards, see	7'3/h'*tf>3/Jl/^§|i|*I^PfT"	(Document format/sample

storage location) on the following page:

https://fuiitsu.sharepoint.com/sites/jp-IKB-sdem/SitePaqes/technoloqy/sdeminformation.aspx

(0 FUJITSU-RESTRICTED )	47	Copyright 2022 FUJITSU LIMITED

The SDEM Practical Standards provide more practical procedures and guides, document formats and

samples, etc., such as Business Application Development and System Infrastructure for each process and category.

Use it to understand practical know-how about work you are in charge of or to determine the document standards for a project.

Copyright 2022 FUJITSU LIMITED

47

(Q FUJITSU-RESTRICTED )

Fufifsu

5. Applying SDEM

What you will understand by the end of this chapter

- Concept of applying SDEM to projects

- Concept and important points of tailoring

- Concept of utilizing SDEM in agile development

Copyright 2022 FUJITSU LIMITED

Chapter 5 explains how to apply SDEM to projects.

By the end of this chapter, you will understand the concept of applying SDEM to projects, the concept and important points of tailoring, and the concept of utilizing SDEM in agile development.

Copyright 2022 FUJITSU LIMITED

48

(Q FUJITSU-RESTRICTED )

5.1 Applying SDEM to Projects	FUJITSU

Tailor and utilize according to project characteristics.

SDEM is a comprehensive structure of work to be done in system construction. SDEM is not premised on a specific application (scale or system form) or implementation means (process model, technique, tool).

Therefore, to apply it to an actual project, tailor (customize the depth of) and utilize the WBS implementation according to the project characteristics.

[Viewpoint of tailoring]

Project Characteristics

System	Technical	Development

Tailoring	Characteristics	Conditions	Conditions

according to 
	project

characteristics

t

Project standards

- Scale	- Development model	- Development

- Application type	(Waterfall, agile,	period

- Core	etc.)	- Skills/Scheme

system/lnformation	- New development,	- Development

system	reconstruction,	form

- Quality	service application	etc.

requirements	- Methods/Tools

etc.	etc.

(0 FUJITSU-RESTRICTED )	Copyright 2022 FUJITSU LIMITED

The first is the concept of applying SDEM to projects.

SDEM is a comprehensive structure of work to be done in system construction. SDEM is not premised on a specific product, system form, or implementation means.

Therefore, to apply it to an actual project, tailoring according to the project characteristics is necessary.

"Tailoring" means to customize the depth of WBS implementation according to project characteristics.

The viewpoints of tailoring include system characteristics, such as the scale and application type, and

conditions such as the development model, new development or reconstruction, skill level, and development form.

Copyright 2022 FUJITSU LIMITED

49

(Q FUJITSU-RESTRICTED )

5.2 Concept of Tailoring	FUJITSU

• WBS tailoring

Tailoring is implemented based on the following concepts.

WBS1	Basically covers the implementation of all WBS

WBS2	Basically covers the implementation of all WBS

WBS3	Selects the WBS to be implemented according to project characteristics

Determines the depth of work to be done

• Integrate and divide phases

Point 1. Do not integrate phases of different processes

As an example, do not integrate the RD phase of the requirement definition process and the Ul phase of the development process, or the ST phase of the development process and the OT phase of the operational test & transition process. The purposes of the phases are different. Make sure the phases are independent of each other regardless of the period length.

Point 2. Divide a phase

If a phase has many system components (business, sub system, etc.) due to the project characteristics, divide the phase.

When dividing a phase and defining the sub phases, make it clear that the purpose of the original phase can be achieved, and clarify the purpose and outline of each sub phase along with its name.

[Example of dividing the IT phase]

IT1 (Inter-program integration test within process), IT2 (Inter-process integration test), ITS (Interface test with external system)

(0 FUJITSU-RESTRICTED*)	50	Copyright2022 FUJITSU LIMITED

Here is an explanation of the concept of tailoring.

In many cases, you will refer to similar projects in the past to determine the project standards. The benefits this will bring include a greater awareness of additional work due to project characteristics or optimization of the formulation of the project standards. On the other hand, there is a risk that the work required for this project will be omitted. Therefore, while referring to past projects, start tailoring based on all WBS of SDEM.

Especially for WBS1 and 2 level work, consider implementing every WBS once.

When deciding against implementation, it is important to be able to explain to a third party why the project requirements can be met without the implementation. An example of a reason is that they are clearly not applicable depending on the project scope.

A careless decision will lead to quality problems.

Depending on the development framework and applied language, for example, you may need to make a choice or review the work at the WBS3 level.

There are special points to keep in mind when integrating or dividing a phase.

For example, depending on the project, the PS and PG phases are integrated in many cases.

However, as an example, do not integrate the RD phase of the requirement definition process and the Ul phase of the development process, or the ST phase of the development process and the OT phase of the operational test & transition process.

The purposes of the phases differ greatly, so it is essential to judge the completion of each phase.

Conversely, it may be better to divide a phase.

For example, by dividing the IT phase into IT 1, IT2, and ITS depending on the scope of integration, you can clarify the purpose to be achieved in each of them, and manage the quality, progress, etc. in divisions.

Copyright 2022 FUJITSU LIMITED

50

(Q FUJITSU-RESTRICTED )

5.3 Concept of Utilizing SDEM in Agile Development	FUJITSU

The work and examination viewpoints defined in the SDEM WBS are the elements 
	required for system development.

Ascertain and utilize the required elements according to the purpose of development.

Agile development

Agile development has no concept of dividing a phase. The actions in each short

development cycle are requirement definition, design, implementation, and testing.

Check requests and repeat implementation in the short cycle to continuously create value.

(0 FUJITSU-RESTRICTED*)	51	Copyright 2022 FUJITSU LIMITED

This chapter ends with an explanation of how to use SDEM in agile development.

Agile development has no concept of dividing a phase. However, the fact remains that requirement definition, design, implementation, and testing are agile actions.

The work and examination viewpoints defined in the SDEM WBS are the elements required for system development.

Ascertain and utilize the required elements flexibly according to the purpose of development in the project.

Copyright 2022 FUJITSU LIMITED

51

(Q FUJITSU-RESTRICTED )

Fufifsu

6. SDEM Usage Scenarios

What you will understand by the end of this chapter

- When to use SDEM

- What can be done with SDEM

- How far the SDEM provision scope extends

- Where to obtain SDEM, and contact information

Copyright 2022 FUJITSU LIMITED

Chapter 6 explains specific SDEM usage scenarios.

By the end of this chapter, you will understand when to use SDEM, what can be done with SDEM, how far the SDEM provision scope extends, and where to obtain SDEM.

Copyright 2022 FUJITSU LIMITED

52

(Q FUJITSU-RESTRICTED )

6.1 Use SDEM at These Times	FUJITSU

• Project manager	What can be done with SDEM

Estimate costs

► Extract the required work, and assume the work volume from the work description j

Create master

schedule

•Plan a scheme by assuming the required skills from the categories corresponding to the

Plan scheme/role 
	division

work, and divide the work

•Extract the work to be performed or approved by the customer, and the perceptions of both 
	parties are aligned beforehand

mm

• Team leader (Business team, system infrastructure team, etc.)

Create detailed 
	schedule

• Team member

Implement initial

• Extract all tasks in the team to create a schedule

QPHHgl

^Content used in relevant scenarios 
	Standard Process

' 
WBS Manual

• Understand the procedure and viewpoints of the work 
work

• Quality auditor in the organization

Create checklist	• Check if some checks were missed in the audit

Structure

WBS1-2-3 data

mm

(0 FUJITSU-RESTRICTED)	Copyright 2022 FUJITSU LIMITED

Here is an explanation of the typical usage scenarios of SDEM for each role. The icons on the right represent the content mainly used in the scenario.

A project manager can use SDEM to estimate costs, create a master schedule, and plan a scheme and role division.

All required work, including that related to the customer, can be extracted. This can be used not only for planning Fujitsu's work but also for planning work where you need to share a common perception with the customer early.

The next page explains an image of planning a scheme and role division using SDEM categories.

The leader of a business team, infrastructure team, or subsystem team can extract all the work in the team by referring to specific WBS work to create a detailed schedule.

Team members will understand the procedure and viewpoints of the work even when experiencing the work for the first time. They will also understand the positioning of their work in the overall work.

SDEM can be used not only in a project but also by quality auditors in the organization. The auditors can check if they missed some checks on a checklist used in the audit.

Copyright 2022 FUJITSU LIMITED

53

(Q FUJITSU-RESTRICTED )

Here is an explanation of an image of specific usage.

The figure on this page is an image showing SDEM usage for planning a project scheme and role division.

The SDEM categories are classified based on the relevance of knowledge and skills required for work. The categories are used to clarify the targets such as application, infrastructure, and operations, and to define the scheme and roles of the project.

As shown in the figure, confirm that all elements in the category, including the customer's scheme, are assigned in order to prevent omissions and gaps in role division.

Copyright 2022 FUJITSU LIMITED

54

(Q FUJITSU-RESTRICTED )

6.3 SDEM Usage Scenario 2) Creating Schedule	FUJITSU

Define the project WBS based on the SDEM WBS, and create work items/schedules.

VP SP

in	b

m c

CA

SDEM-

standard

WBS

I can create schedules effectively without

omitting work items!

New system 
project leader

[New system project] Person-hour estimates/role division/schedule

Work Item	Document	Personnel	Schedule

Collected Work Items

C4UI111 Screen transition design

C4UI112 Screen layout design

Screen transition	Screen transition

design	diagram

Screen layout	Screen layout 
design

Screen item	Screen item

C4UI113 Screen item design	design	definition

C4UI141 Collection of common business messages

Collection of	Business

common business	message list 
messages

(0 FUJITSU-RESTRICTED)	Copyright 2022 FUJITSU LIMITED

Here is an explanation of another image of specific usage. This page explains a usage scenario for creating a schedule.

First, extract the work and output required for the project from the SDEM WBS to create a schedule. Then, you can assign and schedule all the deliverables you need to create.

Copyright 2022 FUJITSU LIMITED

55

(Q FUJITSU-RESTRICTED )

6.4 Scope of SDEM 2.0 Provision	FUJITSU

SDEM is Fujitsu's core technology and important know-how for Fujitsu to outsource SI.

Therefore, provision to an external party is based on the premise that an NDA is concluded and F

JSSSj	Fujitsu is entrusted with SI.	lffHH

SDEM is copyrighted by Fujitsu, and the scope of provision varies depending on the content.

SDEM Structure

Internal Provision 
	Scope

Within

External Provision Scope 
	Business

[Legend] 
V: Can be provided

Company/Group

Standard Process Structure	✓

WBS Manual	✓

SDEM	Standard Process Guide

Standard	(FUJITSU-CONFIDENTIAL)

Customer

Partner

♦ 	♦

♦ 	♦

♦

♦ : Can be provided after the 
	conclusion of a non-disclosure

agreement (NDA), representing a 
confidentiality agreement, on the 
premise that Fujitsu is entrusted 
with SI

x: Cannot be provided or shown

Processes	Standard Process Guide

(for internal use)

WBS1-2-3 work item list (CSV format)

✓

✓

* For the provision scope of the SDEM Practical Standards, see 	{Precautions for Use) on the following page:

httDs://fuiitsu.shareDoint.com/sites/iD-IKB-sdem/SitePaaes/technoloav/attention.asDX

(0 FUJITSU-RESTRICTED )	56	Copyright 2022 FUJITSU LIMITED

Here is an explanation of the scope of provision of SDEM 2.0.

SDEM is Fujitsu's core technology and important know-how for Fujitsu to outsource SI.

Therefore, provision to a customer or business partner is based on the premise that Fujitsu is entrusted with SI.

In addition, a non-disclosure agreement, representing a confidentiality agreement, must be concluded. As shown in the table, some content cannot be provided outside the company.

Furthermore, the scope of provision of the SDEM Practical Standards is determined by content.

When using it, check	JzCD/iSWIl" (Precautions for Use) on the IKB site.

Copyright 2022 FUJITSU LIMITED

56

(Q FUJITSU-RESTRICTED )

6.5 SDEM 2.0 Published by IKB-SDEM	FUJITSU

• A variety of information such as introductory materials and the content introduced in this training 
	course is available on the IKB-SDEM site.

(IKB-SDEM site) https://fuiitsu.sharepoint.com/sites/ip-IKB-sdem/SitePaaes/sdem.aspx

jpmhcQ&iiva

SDEWWMTatt

SDEMSlMlU*

•SDEMlSBe»&!

•Wfes

SDEMt£zMI1>5^

SDEMtSSitSielg-ftWt

SDEM WBSS1R

Pick up

SDEM

H SDEMSfZlfcTMS^v SDEMZI>x>M)

mm?

SDEM2.G

' V	/

IKB-SDEM

FAQ

(J:<*^RPp1)

S D E MI288|-5 F A Q(i’56®CSI<fc"SU,

’ English versions of the 
	following content are

also available:

SDEM Standard 
Processes: Standard 
Process Structure

SDEM Practical Standards: Operation and

Maintenance [ITSMOP]

• For inquiries, please contact us from [Inquiry] on the menu on the IKB-SDEM site.

(0 FUJITSU-RESTRICTED)	57	Copyright 2022 FUJITSU LIMITED

The SDEM content introduced in this training course and the textbooks for this training can be obtained from the IKB-SDEM site. Please make use of them.

For inquiries, please contact us from [Inquiry] on the menu.

The standard process structure "SDEM" is available to provide a system that our customers can use with peace of mind. SDEM is the culmination of Fujitsu SE's wisdom and covers all system development tasks, including the customer ones.

Please use SDEM to work with good quality and without omission.

Copyright 2022 FUJITSU LIMITED

57

(Q FUJITSU-RESTRICTED )

Copyright 2022 FUJITSU LIMITED

58